## Live Conversion
[8 empty] | Short Company Name: | OHG
|  | Yes | Yes | [5 empty] | Trace
|  | No | No | [5 empty] | Joint
?
Task | Notes | Required? (initial set up) | Ongoing import? | Import Source | Type | Routine | Table Name | Routine / Table | Responsible Party | Expected Completion Date | Progress | By | Date Completed | No. of Records | No. of Exceptions | Notes
Infrastructure Set Up - Within Tramps | Preparing the database infrastructure for your needs (or in some cases preparing spreadsheets for trace to load) | [7 empty] | Joint
Security Groups |  | Yes | No |  | Manual | Maintain - System Control - Security Group | N/A | Maintain - System Control - Security Group | Joint |  | Outstanding
Security Group Access | Is 'Routine Security Required' set to 'Yes' in system configuration? | Yes | No |  | Manual | Maintain - System Control - Security Group Access | N/A | Maintain - System Control - Security Group Access | Joint |  | Outstanding
Security Group Permissions | Is 'Routine Security Required' set to 'Yes' in system configuration? | Yes | No |  | Manual | Maintain - System Control - Security Group Permissions | N/A | Maintain - System Control - Security Group Permissions | Joint |  | Outstanding
User security (module) | Give the new security groups access to PM&A and any other modules | Yes | No |  | Manual | Security Manager (module) | N/A | Security Manager (module) | Joint |  | Outstanding
Offices |  | No | N/A |  | Manual | Maintain - System Codes (M..Z) - Office | N/A | Maintain - System Codes (M..Z) - Office | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Manager Codes |  | Yes | No |  | Dataload / Manual? | Maintain - Manager - Details | dev_manager | Maintain - Manager - Details | Joint |  | Outstanding
Workgroups |  | No | N/A |  | Manual | Maintain - System Control - Workgroup | N/A | Maintain - System Control - Workgroup | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Users |  | Yes | No |  | Manual | Maintain - System Control - User Details | N/A | Maintain - System Control - User Details | Joint |  | Outstanding
Amenity Types | Required now if Property / Unit Amenities are to be loaded | No | N/A |  | Manual | Maintain - System Codes (A..L) - Amenity Type | N/A | Maintain - System Codes (A..L) - Amenity Type | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Charge Types | Required for Lease / Headlease records and Lease / Headlease Charge records | Yes | No |  | Manual | Maintain - System Codes (A..L) - Charge Type | SQL Charge Types | Maintain - System Codes (A..L) - Charge Type | Joint |  | Outstanding
Countries | International Standard is GB - United Kingdom | Yes | No |  | Manual | Maintain - System Codes (A..L) - Country Code | N/A | Maintain - System Codes (A..L) - Country Code | Joint |  | Outstanding
Creditor Category Codes |  | No | N/A |  | Manual | Maintain - System Codes (A..L) - Creditor Category | N/A | Maintain - System Codes (A..L) - Creditor Category | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Currencies |  | Yes | No |  | Manual | Maintain - System Codes (A..L) - Currency | N/A | Maintain - System Codes (A..L) - Currency | Joint |  | Outstanding
Debtor Category | Required for Debtor dataload if Debtor Category are being used | ? | No |  | Manual | Maintain - System Codes (A..L) - Debtor Category | N/A | Maintain - System Codes (A..L) - Debtor Category | Joint
Document Types | Required now if Property / Unit documents are to be loaded | ? | No |  | Manual | Maintain - System Codes (A..L) - Document Type | N/A | Maintain - System Codes (A..L) - Document Type | Joint
Due Dates |  | Yes | No |  | Manual / SQL? | Maintain - System Codes (A..L) - Due Date | SQL Due Date Codes | Maintain - System Codes (A..L) - Due Date | Joint |  | Outstanding
Event Types | Diary Events (required if reviews and break options are to be set up in leases) | ? | No |  | Manual | Maintain - System Codes (A..L) - Event Type | N/A | Maintain - System Codes (A..L) - Event Type | Joint
G/L Analysis |  | ? | No |  | Manual | Maintain - System Codes (A..L) - GL Analysis Codes | SQL GL Analysis Codes | Maintain - System Codes (A..L) - GL Analysis Codes | Joint
Lease Types | Required for Lease dataload if Lease Types are being used | ? | No |  | Manual | Maintain - System Codes (A..L) - Lease Type | N/A | Maintain - System Codes (A..L) - Lease Type | Joint
Location Codes | Required for Property dataload if Location Codes are being used | ? | No |  | Manual | Maintain - System Codes (A..L) - Location | N/A | Maintain - System Codes (A..L) - Location | Joint
Measurement Reason | Required now if Property / Unit measurements are to be loaded | ? | No |  | Manual | Maintain - System Codes (M..Z) - Measurement Reason | N/A | Maintain - System Codes (M..Z) - Measurement Reason | Joint
Note Subject | Required now if Property / Unit notes are to be loaded | ? | No |  | Manual | Maintain - System Codes (M..Z) - Note Subject | N/A | Maintain - System Codes (M..Z) - Note Subject | Joint
Property Analysis Codes | Required for Property dataload if Property analysis is being used | ? | No |  | Manual | Maintain - System Codes (M..Z) - Property Analysis | N/A | Maintain - System Codes (M..Z) - Property Analysis | Joint
Property Group Codes | Required for Property dataload if Property groups are being used | ? | No |  | Manual | Maintain - System Codes (M..Z) - Property Group | N/A | Maintain - System Codes (M..Z) - Property Group | Joint
Property Status Category |  | ? | No |  | Manual | Maintain - System Codes (M..Z) - Property Status Category | N/A | Maintain - System Codes (M..Z) - Property Status Category | Joint
Property Type Codes | Required for Property dataload if Property Types are being used | ? | No |  | Dataload / Manual? | Maintain - System Codes (M..Z) - Property Type | dev_property_type | Maintain - System Codes (M..Z) - Property Type | Joint
Regions |  | ? | No |  | Manual | Maintain - System Codes (M..Z) - Region | N/A | Maintain - System Codes (M..Z) - Region | Joint
Service Type Codes | For Supplier and Payment Selection | ? | No |  | Manual | Maintain - System Codes (M..Z) - Service Type | N/A | Maintain - System Codes (M..Z) - Service Type | Joint
Site | Required for Property dataload if Sites are being used | ? | No |  | Manual | Maintain - System Codes (M..Z) - Site | N/A | Maintain - System Codes (M..Z) - Site | Joint
Sub Analysis |  | ? | No |  | Manual | Maintain - System Codes (M..Z) - Sub Analysis Codes | SQL Sub Analysis Codes | Maintain - System Codes (M..Z) - Sub Analysis Codes | Joint
Unit Group Codes | Required for unit dataload if unit groups are being used | ? | No |  | Manual | Maintain - System Codes (M..Z) - Unit Group | N/A | Maintain - System Codes (M..Z) - Unit Group | Joint
Usage Types | Required for lease dataload if usage types are being used (on the Tenancy Tab) | ? | No |  | Manual | Maintain - System Codes (M..Z) - Usage Type | N/A | Maintain - System Codes (M..Z) - Usage Type | Joint
Valuation Method | Required now if Property/Unit Valuations are to be loaded | ? | No |  | Manual | Maintain - System Codes (M..Z) - Valuation Method | N/A | Maintain - System Codes (M..Z) - Valuation Method | Joint
Valuation Office | Required now if Property/Unit Rating Information is to be loaded | ? | No |  | Manual | Maintain - System Codes (M..Z) - Valuation Office | N/A | Maintain - System Codes (M..Z) - Valuation Office | Joint
Valuation Reason | Required now if Property/Unit Valuations are to be loaded | ? | No |  | Manual | Maintain - System Codes (M..Z) - Valuation Reason | N/A | Maintain - System Codes (M..Z) - Valuation Reason | Joint
VAT Rate Codes |  | Yes | No |  | Manual | Maintain - System Codes (M..Z) - VAT Rate | N/A | Maintain - System Codes (M..Z) - VAT Rate | Joint |  | Outstanding
System Configuration | Inc. folder locations | Yes | No |  | Manual | Maintain - System Control - System Configuration | N/A | Maintain - System Control - System Configuration | Joint |  | Outstanding |  |  | 1 | 0
Expense Categories |  | ? | No |  | Manual | Maintain - Accounts - Property Expense Category | N/A | Maintain - Accounts - Property Expense Category | Joint
Expense Codes |  | ? | No |  | Manual / SQL? | Maintain - Accounts - Property Expense | SQL Expense Codes | Maintain - Accounts - Property Expense | Joint
Sub Ledgers |  | ? | No |  | Manual | Maintain - Accounts - Sub-Ledger | N/A | Maintain - Accounts - Sub-Ledger | Joint
Authorities |  | ? | No |  | Manual | Maintain - Parties - Authority | N/A | Maintain - Parties - Authority | Joint
Bank |  | ? | No |  | Manual | Maintain - System Codes (A..L) - Bank | N/A | Maintain - System Codes (A..L) - Bank | Joint
Bank Branch |  | ? | No |  | Manual | Maintain - System Codes (A..L) - Bank Branch | N/A | Maintain - System Codes (A..L) - Bank Branch | Joint
Bank Chart Codes |  | ? | No |  | Manual | Maintain - Accounts - Chart | SQL Bank Chart Codes | Maintain - Accounts - Chart | Joint
Bank Account ID |  | ? | No |  | Manual | Maintain - System Codes (A..L) - Bank Account | SQL Bank Account IDs | Maintain - System Codes (A..L) - Bank Account | Joint
Other Chart Codes |  | ? | No |  | Manual | Maintain - Accounts - Chart | SQL Other Chart Codes | Maintain - Accounts - Chart | Joint
Transaction Types |  | ? | No |  | Manual | Maintain - Accounts - Transaction Type | SQL Transaction Types | Maintain - Accounts - Transaction Type | Joint
System Accounting Parameters | Some chart codes and transaction types required for this | Yes | No |  | Manual | Maintain - Accounts - System Accounting Parameters | N/A | Maintain - Accounts - System Accounting Parameters | Joint |  | Outstanding |  |  | 1 | 0
Parent Company |  | ? | ? |  | Manual | Maintain - Parties - Parent Company | N/A | Maintain - Parties - Parent Company | Joint
Static Data | Preparing spreadsheets of your static data for dataload (or in some cases inputting manually) | [7 empty] | OHG
Company Creditors |  | ? | ? |  | Dataload / Manual? | Maintain - Accounts - Creditor | dev_creditor | Maintain - Accounts - Creditor | OHG
Companies | Companies can be set up from Company Creditor Dataload Process | Yes | Yes | UH Import | Dataload | Maintain - Parties - Company | dev_Company | dev_Company | OHG |  | Outstanding
Company Accounts |  | Yes | Yes | Generate from Company import | Dataload | Maintain - Accounts - Company - Account Details | SQL Company Accounts |  | OHG |  | Outstanding
Period Accounts |  | Yes | Yes | Generate from Company import | Dataload | Maintain - Accounts - Period Account | dev_period_date | dev_period_date | OHG |  | Outstanding
Participant Creditors |  | No | N/A |  | N/A | Maintain - Accounts - Creditor | dev_creditor | Maintain - Accounts - Creditor | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Participants | Can be generated from Participant Creditor Dataload. Cannot be Dataloaded separately. | No | N/A |  | N/A | Maintain - Parties - Participant | Generated from Participant Creditor | Maintain - Parties - Participant | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Estate |  | Yes | Yes | UH Import | SQL | Maintain - Property - Estate | N/A |  | OHG |  | Outstanding
Properties |  | Yes | Yes | UH Import | Dataload | Maintain - Property - Details | dev_property | dev_property | OHG |  | Outstanding
Property Accounts | Automatically set up from Company a/c record (provided that is set up first) | Yes | Yes | Generate from Property import | Dataload (Auto) | Maintain - Accounts - Property Account | dev_property _accounting | Maintain - Accounts - Property Account | OHG |  | Outstanding
Property Capital Valuation |  | No | N/A |  | N/A | Maintain - Property - Capital Valuation | dev_property _capital_valuation | Maintain - Property - Capital Valuation | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Property Diary |  | No | N/A |  | N/A | Maintain - Property - Diary | dev_property _diary | Maintain - Property - Diary | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Property Documents |  | No | N/A |  | N/A | Maintain - Property - Document | dev_property _document | Maintain - Property - Document | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Property Measurement Totals |  | No | N/A |  | N/A | Maintain - Property - Measurement | dev_property _measurement | Maintain - Property - Measurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Property Notes |  | No | N/A |  | N/A | Maintain - Property - Note | dev_property _note | Maintain - Property - Note | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Property Purchase & Sale |  | No | N/A |  | N/A | Maintain - Property - Purchase & Sale | dev_property _purchase_sale | Maintain - Property - Purchase & Sale | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Rating Information |  | No | N/A |  | N/A | Maintain - Property - Rating Information | dev_property _rating | Maintain - Property - Rating Information | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Property to Manager |  | Yes | ? | Generate from Property import? | Dataload | Maintain - Property - To Manager | dev_property _to_manager | dev_property _to_manager | OHG |  | Outstanding
Property Valuation |  | No | N/A |  | N/A | Maintain - Property - Valuation | dev_property _valuation | Maintain - Property - Valuation | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Units |  | Yes | Yes | UH Import | Dataload | Maintain - Unit - Details | dev_unit | dev_unit | OHG |  | Outstanding
Unit Diary |  | No | N/A |  | N/A | Maintain - Unit - Diary | dev_unit_diary | Maintain - Unit - Diary | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unit Documents |  | No | N/A |  | N/A | Maintain - Unit - Document | dev_unit_document | Maintain - Unit - Document | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unit Measurement Totals |  | No | N/A | NB/ Soc Rent 1999 Valuation set on unit record | N/A | Maintain - Unit - Measurement | dev_unit_measurement | Maintain - Unit - Measurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unit Notes |  | No | N/A |  | Dataload / Manual? | Maintain - Unit - Note | dev_unit_note | Maintain - Unit - Note | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unit Purchase & Sale |  | No | N/A |  | Dataload / Manual? | Maintain - Unit - Purchase & Sale | dev_unit_purchase_sale | Maintain - Unit - Purchase & Sale | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unit Rating Information |  | No | N/A |  | Dataload / Manual? | Maintain - Unit - Rating Information | dev_unit_rating | Maintain - Unit - Rating Information | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Unit Valuation |  | No | N/A |  | Dataload / Manual? | Maintain - Unit - Valuation | dev_unit_valuation | Maintain - Unit - Valuation | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Tenants |  | Yes | Yes | 'Combined' UH Import Tenant/Lease/Debtor | Dataload | Maintain - Parties - Tenant | dev_tenant | dev_tenant | OHG |  | Outstanding
Leases | Debtor Records can be generated by the lease dataload and linked to the generated charges | Yes | Yes | 'Combined' UH Import Tenant/Lease/Debtor (also additional generated records relating to lease) + must include indexation | Dataload | Maintain - Lease - Details | dev_lease | dev_lease | OHG |  | Outstanding
Tenancy Notes | Tenant and Lease must exist | No | N/A |  | Dataload / Manual? | Maintain - Lease - Tenancy Note | dev_tenancy_note | Maintain - Lease - Tenancy Note | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Debtors | Only required if debtors are not generated by the lease dataload. | Yes | Yes | 'Combined' UH Import Tenant/Lease/Debtor | Dataload | Maintain - Accounts - Debtor Details | dev_debtor | dev_debtor | OHG |  | Outstanding
Debtor Bank Details | For Direct Debit Bank Details of Debtors | No | N/A |  | N/A | Maintain - Accounts - Debtor - Debtor Bank | dev_debtor_bank | Maintain - Accounts - Debtor - Debtor Bank | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
(Additional) Lease Charges | The main lease charges will be generated from the lease records | No | N/A | Probably not required | Dataload / Manual? | Maintain - Lease - Charge | dev_lease_charge | Maintain - Lease - Charge | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Lease Charge History | Historic changes to regular charges on the lease. | No | N/A | Lease charge history will be updated by new charges (but no historic charges will be loaded) | N/A | Maintain - Lease - Charge History | dev_lease_charge_history | Maintain - Lease - Charge History | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Lease Notes | Notes records associated with a lease | No | N/A |  | Dataload / Manual? | Maintain - Lease - Note | dev_lease_note | Maintain - Lease - Note | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Landlords |  | No | N/A |  | N/A | Maintain - Parties - Landlord | dev_landlord | Maintain - Parties - Landlord | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Head Leases |  | No | N/A |  | N/A | Maintain - Head Lease - Details | dev_head_lease | Maintain - Head Lease - Details | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
(Additional) Head Lease Charges | The main head lease charges will be generated from the lease records | No | N/A |  | N/A | Maintain - Head Lease - Charge | SQL Head Lease Charge | Maintain - Head Lease - Charge | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Head Lease Charge History | Historic changes to regular charges on the head lease. | No | N/A |  | N/A | Maintain - Head Lease - Charge History | dev_head_lease_charge_history | Maintain - Head Lease - Charge History | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Head Lease Notes | Notes records associated with a head lease | No | N/A |  | N/A | Maintain - Head Lease - Note | dev_head_lease_note | Maintain - Head Lease - Note | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Company level Chart Codes | Which Chart Codes need to be linked to which Companies for which subledgers? Company level may only relate to bank chart codes for banking rules | Yes | Yes | Generate for new company | List | Process - Account Maintenance - (Multiple/Template/Bulk Account…) | N/A | Process - Account Maintenance - (Multiple/Template/Bulk Account…) | OHG |  | Outstanding
Property level Chart Codes | Which Chart Codes need to be linked to which properties for which subledgers? | Yes | Yes | Generate for new property | List | Process - Account Maintenance - (Multiple/Template/Bulk Account…) | N/A | Process - Account Maintenance - (Multiple/Template/Bulk Account…) | OHG |  | Outstanding
Banking Rules | Chart codes must be linked to relevant properties /Companies | Yes | Yes | Generate for new company / property | Dataload / Manual? | Maintain - Accounts - Banking Rules | dev_banking_rules | Maintain - Accounts - Banking Rules | OHG |  | Outstanding
Property Expense Schedules | Property account records must exist | Yes | Yes | Initial import from spreadsheets - update in BlueBox / Dataload? | SQL | Maintain - Accounts - Property Expense Shedule | SQL Property Expense Schedule | SQL Property Expense Schedule | OHG |  | Outstanding
Property Expense Analysis | Possible 'standard' list for non recoverable expenditure. | Yes | Yes | Initial import from spreadsheets - update in BlueBox / Dataload? | SQL | Maintain - Accounts - Property Expense Analysis | SQL Property Expense Analysis | SQL Property Expense Analysis | OHG |  | Outstanding |  |  |  |  | You may wish to set up Analysis for one property and then use the Property Expense Analysis Template Process to copy that to your other properties.
Property Expense Analysis (2) | S/C Recoverable Analysis | Yes | Yes | Initial import from spreadsheets - update in BlueBox / Dataload? | SQL | Maintain - Accounts - Property Expense Analysis | SQL Property Expense Analysis | SQL Property Expense Analysis | OHG |  | Outstanding
Unit Apportionment | Property expense schedules must exist | Yes | Yes | Initial import from spreadsheets - update in BlueBox / Dataload? | Dataload | Maintain - Unit - Apportionment | dev_unit_apportionment | dev_unit_apportionment | OHG |  | Outstanding
Supplier Creditors |  | Yes | Yes | 'Combined' PIP/SUN import Supplier/Creditor | Dataload | Maintain - Accounts - Creditor | dev_creditor | dev_creditor | OHG |  | Outstanding
Suppliers | Supplier can be set up from Supplier Creditor Dataload Process | Yes | Yes | 'Combined' PIP/SUN import Supplier/Creditor | Dataload | Maintain - Parties - Supplier | dev_supplier | dev_supplier | OHG |  | Outstanding
Service Charge Periods |  | Yes | Yes | Generate from Property import | SQL | Process - Service Charges - S/C Period | SQL Service Charge Periods | SQL Service Charge Periods | OHG |  | Outstanding
Service Charge Budget Periods | Defaults to the service charge period (only required if multiple periods per S/C year to be set up) | Yes | Yes | Generate from Property import | SQL | Process - Service Charges - S/C Task | SQL Service Charge Budget Periods | SQL Service Charge Budget Periods | OHG |  | Outstanding
Service Charge Budgets | S/C Periods and S/C Budget periods must exist | ? | ? |  | Dataload | Process - Service Charges - S/C Task | dev_property_budget | dev_property_budget | OHG
Management Fees |  | No | ? |  | N/A | Maintain - Accounts - Management Fee Rules | SQL Management Fee Rules | Maintain - Accounts - Management Fee Rules | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Transactional Data | [8 empty] | OHG
Debtor Opening Items |  | No | ? |  | N/A |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Opening Cash Balances |  | No | ? |  | N/A |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Creditor Opening Items (invoice batch) | Creditor Invoice Batch - Post with a transaction type which will not show as expenditure | No | ? |  | N/A |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Service Charge Opening Expenditure | If going live part way through a service charge year | Yes | ? |  | Dataload |  |  |  | OHG |  | Outstanding
Service Charge opening on A/C's | If going live part way through a service charge year | Yes | ? |  | Dataload |  |  |  | OHG |  | Outstanding
Not Time-Critical: - | [8 empty] | OHG
Manager Types |  | Yes | No |  | Manual | Maintain - Management Type | N/A | Maintain - Management Type | OHG |  | Outstanding
Property to Participant |  | No | N/A |  | Manual | Maintain - Property - To Participant | N/A | Maintain - Property - To Participant | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Address Category | ? | No | N/A |  | Manual | Maintain - System Codes (A..L) - Address Category | N/A | Maintain - System Codes (A..L) - Address Category | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Alternative Descriptions | For other languages | No | N/A |  | Manual | Maintain - System Codes (A..L) - Alternative Descriptions | N/A | Maintain - System Codes (A..L) - Alternative Descriptions | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Area Type | ? | No | N/A |  | Manual | Maintain - System Codes (A..L) - Area Type | N/A | Maintain - System Codes (A..L) - Area Type | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Bank Interest Rate |  | No | N/A |  | Manual | Maintain - System Codes (A..L) - Bank Interest Rate | N/A | Maintain - System Codes (A..L) - Bank Interest Rate | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Business Rate | ? | No | N/A |  | Manual | Maintain - System Codes (A..L) - Business Rate | N/A | Maintain - System Codes (A..L) - Business Rate | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Contact Type | For Related Contacts | No | N/A |  | Manual | Maintain - System Codes (A..L) - Contact Type | N/A | Maintain - System Codes (A..L) - Contact Type | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Correspondance Category | For Debtor, Creditor & Company Correspondance | No | N/A |  | Manual | Maintain - System Codes (A..L) - Correspondance Category | N/A | Maintain - System Codes (A..L) - Correspondance Category | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Currency Rate | For currency conversion | No | N/A |  | Manual | Maintain - System Codes (A..L) - Correspondance Category | N/A | Maintain - System Codes (A..L) - Correspondance Category | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Debt Status | For assigning a status to oustanding debtor items | No | N/A |  | Manual | Maintain - System Codes (A..L) - Correspondance Category | N/A | Maintain - System Codes (A..L) - Correspondance Category | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Document Delivery Defaults | For email wording. | No | N/A |  | Manual | Maintain - System Control - Document Delivery Defaults | N/A | Maintain - System Control - Document Delivery Defaults | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Income tax |  | No | N/A |  | Manual | Maintain - System Codes (A..L) - Income tax | N/A | Maintain - System Codes (A..L) - Income tax | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Inflation Profile |  | No | N/A |  | Manual | Maintain - System Codes (A..L) - Inflation Profile | N/A | Maintain - System Codes (A..L) - Inflation Profile | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Inflation Details |  | No | N/A |  | Manual | Maintain - System Codes (A..L) - Inflation Profile Details | N/A | Maintain - System Codes (A..L) - Inflation Profile Details | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Languages |  | No | N/A |  | Manual | Maintain - System Codes (A..L) - Language | N/A | Maintain - System Codes (A..L) - Language | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Letters in the Arrears Letter Cycle(s) |  | No | N/A |  | Manual | Maintain - System Codes (A..L) - Letter | N/A | Maintain - System Codes (A..L) - Letter | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Arrears Letter Cycle(s) |  | No | N/A |  | Manual | Maintain - System Codes (A..L) - Letter Series | N/A | Maintain - System Codes (A..L) - Letter Series | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Meter Charge Band |  | No | N/A |  | Manual | Maintain - System Codes (M..Z) - Meter Charge Band | N/A | Maintain - System Codes (M..Z) - Meter Charge Band | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Price Index Name |  | Yes | N/A |  | Manual | Maintain - System Codes (M..Z) - Price Index Name | N/A | Maintain - System Codes (M..Z) - Price Index Name | OHG |  | Outstanding
Price Index Values |  | Yes | No | Ongoing values input manually | Manual | Maintain - System Codes (M..Z) - Price Index Values | N/A | Maintain - System Codes (M..Z) - Price Index Values | OHG |  | Outstanding
Report Set |  | No | N/A |  | Manual | Maintain - System Codes (M..Z) - Report Set | N/A | Maintain - System Codes (M..Z) - Report Set | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Arrears Templates |  | No | N/A |  | Manual | Maintain - System Codes (M..Z) - Template | N/A | Maintain - System Codes (M..Z) - Template | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Other Letter Templates |  | No | N/A |  | Manual | Maintain - System Codes (M..Z) - Template | N/A | Maintain - System Codes (M..Z) - Template | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Time Zone |  | No | N/A |  | Manual | Maintain - System Codes (M..Z) - Time Zone | N/A | Maintain - System Codes (M..Z) - Time Zone | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Public Holidays |  | Yes | No |  | Import Process | Tools - Import Public Holiday | N/A | Tools - Import Public Holiday | OHG |  | Outstanding

## Entities (hidden)
Entity | Required fields
Company | Company ref | Company Name | Search Name
| Auto gen |  | UH Company ref | Plus address fields etc optional
Company Account | Company ref | Current Year End
| from company record | Next 31/03 | Could provide remainder via a dummy company template
Period Accounts | Company ref | Start date | End Date | Open Period | Period Label
| from company record | Last 01/04 | Next 31/03 | 'Current' | Genarated
|  | Next 01/04 | Following 31/03 | 'Open' | Genarated
Estate | Estate Ref
Auto Generate*
| UH Ref | UH Unit | UH Property
| BHE43352/02 | 12345

## Company
| Mandatory Field | Required (For OHG) | Source | Predefined Values | UH Field | Format | Comments | newint
Ref | Yes | Yes | Auto Populate |  |  | N/A
Default Currency Code | Yes | Yes | Predefined | GBP |  | N/A
Name | Yes | Yes | UH |  | supplier.sup_name | Varchar(45)
Search Name |  | Yes | UH |  | supplier.sup_ref | Varchar(20) | Unsure of this. Left in for testing though.
Building Name |  | Yes | UH |  | supplier.post_desig | Varchar(40) | Not in UH
Road Number |  | Yes | UH |  | supplier.post_desig | Varchar(40)
Road Name 1 |  | Yes | UH |  | supplier.address | Varchar(40) | Address in UH is all on one line so created column called address
Road Name 2 |  | Yes | UH |  |  | Varchar(40) | Address in UH is all on one line so created column called address
Town |  | Yes | UH |  |  | Varchar(40) | Address in UH is all on one line so created column called address
County |  | Yes | UH |  |  | Varchar(40) | Address in UH is all on one line so created column called address
Postcode |  | Yes | UH |  | supplier.post_code | Varchar(10)
Country Code |  | No | N/A |  |  | N/A
Allow multiple Countries at Property level |  | No | N/A |  |  | N/A
Phone |  | No | N/A |  |  | Varchar(20)
Direct Phone |  | No | N/A |  |  | Varchar(20)
Mobile Phone |  | No | N/A |  |  | Varchar(20)
Fax |  | No | N/A |  |  | Varchar(20)
Contact Name |  | No | N/A |  |  | Varchar(45)
Company Parent Ref |  | No | N/A |  |  | N/A
Email |  | No | N/A |  |  | Varchar(50)
Fico Reg No |  | No | N/A |  |  | N/A
Fico Status |  | No | N/A |  |  | N/A
Fico Approval Date |  | No | N/A |  |  | N/A
VAT Prefix |  | Yes | UH |  | (e.g. GB) | Varchar(2) | Not in UH
VAT Reg No |  | Yes | UH |  | ? | Varchar(9) | Not in UH
Registered Company No |  | Yes | UH |  | ? | Varchar(12) | Not in UH
Remittance Contact Name |  | No | N/A |  |  | N/A
Remittance Fax |  | No | N/A |  |  | N/A
Remittance Email |  | No | N/A |  |  | N/A
Remittance Preferred Method of Contact |  | No | N/A |  |  | N/A
Demands Contact Name |  | No | N/A |  |  | N/A
Demands Email |  | No | N/A |  |  | N/A
Demands Fax |  | No | N/A |  |  | N/A
Demands Preferred Method of Contact |  | No | N/A |  |  | N/A
Client Statement Contact Name |  | No | N/A |  |  | N/A
Client Statement Email |  | No | N/A |  |  | N/A
Client Statement Fax |  | No | N/A |  |  | N/A
Client Statement Preferred Method of Contact |  | No | N/A |  |  | N/A
Default Property Status Category |  | No | N/A |  |  | N/A
Default As At |  | No | N/A |  |  | N/A

## Company Account
A Template of values could be used for this table | Mandatory Field | Required (For OHG) | Source | Predefined Values | UH Field | Format | Comments
Client Ref | Yes | Yes | Company Table
Current Year End Date | Yes | Yes | UH |  |  | dd/mm/yyyy
Retained Profit Chart Code |  |  | Predefined (Template?) | TBC
Tenant Invoice Style | Yes | Yes | Predefined (Template?) | TBC
Default System Logo Used | Yes | Yes | Predefined (Template?) | TBC
Client Logo For Demands |  |  | Predefined (Template?) | TBC
Stop All Postings |  |  | Predefined (Template?) | TBC
Stop Charge Raising |  |  | Predefined (Template?) | TBC
Stop Demand Production |  |  | Predefined (Template?) | TBC
Stop Head Lease Payment Production |  |  | Predefined (Template?) | TBC
Valid From Date |  |  | Predefined (Template?) | TBC
Valid To Date |  |  | Predefined (Template?) | TBC
Banking Rules |  |  | Predefined (Template?) | TBC
Inter Client Cash Transfers |  |  | Predefined (Template?) | TBC
Summary Balance Report Set Code |  |  | Predefined (Template?) | TBC
Accounts Must Use Sub-Ledger |  |  | Predefined (Template?) | TBC
Automated Management Fees |  |  | Predefined (Template?) | TBC
Management Fee Level |  |  | Predefined (Template?) | TBC
RICS Applies |  |  | Predefined (Template?) | TBC
Funds Test Level |  |  | Predefined (Template?) | TBC
Combine Bank Balances |  |  | Predefined (Template?) | TBC
Combine Sub Ledgers |  |  | Predefined (Template?) | TBC
Check Overall Client Balances |  |  | Predefined (Template?) | TBC
Funds Test At Client Parent |  |  | Predefined (Template?) | TBC
Accrual Method |  |  | Predefined (Template?) | TBC
Split Invoice Allocation |  |  | Predefined (Template?) | TBC
Base Currency Code |  |  | Predefined (Template?) | TBC
Suspense Bank Account ID |  |  | Predefined (Template?) | TBC
Common Receipts Cash Control |  |  | Predefined (Template?) | TBC
Common Payments Cash Control |  |  | Predefined (Template?) | TBC
Inter Company Cash Control Code |  |  | Predefined (Template?) | TBC
S/C Liability Chart Code |  |  | Predefined (Template?) | TBC
Loss On S/C Chart Code |  |  | Predefined (Template?) | TBC
S/C Journal Transaction Type |  |  | Predefined (Template?) | TBC
Service Charge Journal Usage |  |  | Predefined (Template?) | TBC
Currency Difference Chart Code |  |  | Predefined (Template?) | TBC
Float Retained Chart Code |  |  | Predefined (Template?) | TBC
Direct to Client Chart Code |  |  | Predefined (Template?) | TBC
Ini Settings |  |  | Predefined (Template?) | TBC
Demand Format |  |  | Predefined (Template?) | TBC
Demand Language |  |  | Predefined (Template?) | TBC
Document Title |  |  | Predefined (Template?) | TBC
Separate Title on Negative Docs |  |  | Predefined (Template?) | TBC
Credit Document Title |  |  | Predefined (Template?) | TBC
Interest Text |  |  | Predefined (Template?) | TBC
Void Funding Demands By |  |  | Predefined (Template?) | TBC
Next Invoice Ref |  |  | Predefined (Template?) | TBC
Next Demand Ref |  |  | Predefined (Template?) | TBC
Print Name |  |  | Predefined (Template?) | TBC
Print Address |  |  | Predefined (Template?) | TBC
Only if Residential |  |  | Predefined (Template?) | TBC
Print VAT No |  |  | Predefined (Template?) | TBC
Print Notice Address |  |  | Predefined (Template?) | TBC
Print Acting As |  |  | Predefined (Template?) | TBC
Suppress Unchanged Lease Charges |  |  | Predefined (Template?) | TBC
Print Without Prejudice |  |  | Predefined (Template?) | TBC
Print Payments To |  |  | Predefined (Template?) | TBC
Print Bank Account Number |  |  | Predefined (Template?) | TBC
Print Interest Text |  |  | Predefined (Template?) | TBC
Print Due Date |  |  | Predefined (Template?) | TBC
Use Contact on Demands |  |  | Predefined (Template?) | TBC
Print Reason for Change |  |  | Predefined (Template?) | TBC
Print Optional Text |  |  | Predefined (Template?) | TBC
Property Level Permitted |  |  | Predefined (Template?) | TBC
Date Type |  |  | Predefined (Template?) | TBC
Include All Sub-Ledger Codes |  |  | Predefined (Template?) | TBC
Sub-Ledger Code List |  |  | Predefined (Template?) | TBC
Include Blank Sub-Ledger Code |  |  | Predefined (Template?) | TBC
Format Override Permitted |  |  | Predefined (Template?) | TBC
Print Client Totals |  |  | Predefined (Template?) | TBC
Client Statement Extract For Client |  |  | Predefined (Template?) | TBC
Bank Account by Sub-Ledger |  |  | Predefined (Template?) | TBC
Summary by Sub-Ledger |  |  | Predefined (Template?) | TBC
Account Within Sub-Ledger |  |  | Predefined (Template?) | TBC
Sub-Ledger Within Account |  |  | Predefined (Template?) | TBC
DC Analyse by Sub-Ledger Code |  |  | Predefined (Template?) | TBC
Analyse by General Ledger Code |  |  | Predefined (Template?) | TBC
Analyse by Chart Code |  |  | Predefined (Template?) | TBC
DC Print VAT Details |  |  | Predefined (Template?) | TBC
Print Demand No |  |  | Predefined (Template?) | TBC
CC Analyse by Sub-Ledger Code |  |  | Predefined (Template?) | TBC
Analyse by Transaction Type |  |  | Predefined (Template?) | TBC
CC Print VAT Details |  |  | Predefined (Template?) | TBC
Show True VAT |  |  | Predefined (Template?) | TBC
Suppress Expenditure Transaction Report |  |  | Predefined (Template?) | TBC
CIS Applies |  |  | Predefined (Template?) | TBC
Agent Acts as Contractor |  |  | Predefined (Template?) | TBC
CIS Registration Number |  |  | Predefined (Template?) | TBC
Registration From Date |  |  | Predefined (Template?) | TBC
Registraion Expiry Date |  |  | Predefined (Template?) | TBC
EDI Identification |  |  | Predefined (Template?) | TBC
Default Revenue Creditor Account No |  |  | Predefined (Template?) | TBC
Default Tax Deduction Trans Type Code |  |  | Predefined (Template?) | TBC
CIS Concession Limit |  |  | Predefined (Template?) | TBC
Employers Tax Reference |  |  | Predefined (Template?) | TBC
Unique Taxpayer Reference |  |  | Predefined (Template?) | TBC
Accounts Office Reference No |  |  | Predefined (Template?) | TBC
Generate R&C VAT Payable |  |  | Predefined (Template?) | TBC
R&C Client Liability Chart Code |  |  | Predefined (Template?) | TBC
R&C Creditor Control Chart Code |  |  | Predefined (Template?) | TBC
R&C Creditor Account No |  |  | Predefined (Template?) | TBC
R&C VAT Rate Code |  |  | Predefined (Template?) | TBC
Automated Payments to Client |  |  | Predefined (Template?) | TBC
Property Use Client Flag |  |  | Predefined (Template?) | TBC
Transaction Type Code |  |  | Predefined (Template?) | TBC
Property Transaction Type Code |  |  | Predefined (Template?) | TBC
Pay To Cli Creditor Account No |  |  | Predefined (Template?) | TBC
Retained VAT |  |  | Predefined (Template?) | TBC
Use Actual Bank |  |  | Predefined (Template?) | TBC
Include Unapplied Cash |  |  | Predefined (Template?) | TBC
Include Released Payables |  |  | Predefined (Template?) | TBC
Released Payables Days After |  |  | Predefined (Template?) | TBC
Include Approved Payables |  |  | Predefined (Template?) | TBC
Approved Payables Days After |  |  | Predefined (Template?) | TBC
Include Logged Payables |  |  | Predefined (Template?) | TBC
Logged Payables Days After |  |  | Predefined (Template?) | TBC
Include Credit Notes |  |  | Predefined (Template?) | TBC
Include Overall Credit Balances |  |  | Predefined (Template?) | TBC
Include Approved POM Invoices |  |  | Predefined (Template?) | TBC
POM Invoices Days After |  |  | Predefined (Template?) | TBC
Include POM Orders |  |  | Predefined (Template?) | TBC
Include NRL Tax Liability |  |  | Predefined (Template?) | TBC
Payments To Participants |  |  | Predefined (Template?) | TBC
Social Rent Default % Tolerance |  | Yes | Predefined (Template?) | TBC |  |  | New

## Estate
| Mandatory Field | Required (For OHG) | Source | Predefined Values | UH Field | Format | Comments
Ref | Yes | Yes | Auto Generate |  | property.estate | N/A
Name | Yes | Yes | UH |  | lookup.lu_desc | Varchar(45) | LOOKUP: SELECT lu_ref, lu_type, lu_desc FROM lookup AS l1 WHERE (lu_type = 'uES')) AS ure ON property.u_estate = ure.lu_ref
Search Name |  | Yes | UH |  |  | Varchar(20)
Tenure |  | No | N/A |  |  | Fixed List of Values
Building Name |  | No | N/A |  |  | Varchar(40)
Road Number |  | No | N/A |  |  | Varchar(40)
Road Name 1 |  | No | N/A |  |  | Varchar(40)
Road Name 2 |  | No | N/A |  |  | Varchar(40)
Town |  | No | N/A |  |  | Varchar(40)
County |  | No | N/A |  |  | Varchar(40)
Postcode |  | No | N/A |  |  | Varchar(10)
Country Code |  | No | N/A |  |  | N/A
Manager Code | Yes | Yes | UH |  | ? | 5 digit code for the manager (code must exist in Bluebox) | ACTIV or INACT
Default Currency Code | Yes | Yes | Predefined | GBP |  | N/A

## Property
UH Block | Mandatory Field | Required (For OHG) | N/A | Predefined Values | UH Field | Format | Comments |  | New Int
Ref | Yes | Yes | Auto Generate |  | ? | N/A |  |  | Ref | TRUE | Ref
Company Ref | Yes | Yes | Company Table |  | ? | N/A | Lookup the company ref based on UH supplying the UH company Ref |  | Company Ref | TRUE | Company Ref
Manager Code | Yes | Yes | UH |  | ? | 5 digit code for the manager (code must exist in Bluebox) | Is this agent? |  | Manager Code | TRUE | Manager Code
Default Currency Code | Yes | Yes | Predefined | GBP |  | N/A |  |  | Default Currency Code | TRUE | Default Currency Code
Name | Yes | Yes | UH |  | Block Name ? | Varchar(40) | ANL name? |  | Name | TRUE | Name
Search Name |  | Yes | UH |  | (UH Block ref) major_ref | Varchar(20) |  |  | Search Name | TRUE | Search Name
Service Charges | Yes | Yes | UH |  | (add to UH) | None, Payable, Receivable, Paid&Recvd | OHG will use 'Receivable' (possibly 'None' on ocassions) (eligible or ineligible or any SC= Receivable) |  | Service Charges | TRUE | Service Charges
Tenure |  | Yes | UH |  | rent.tenure | Freehold, Leasehold, Mixed, Unknown, Flying Freehold or Memorandum of Terms of Occupation. | But brings up multiple results that do not fit the format given. Talk to Alan |  | Tenure | TRUE | Tenure
Building Name |  | Yes | UH |  | property.post_preamble | Varchar(40) |  |  | Building Name | TRUE | Building Name
Road Number |  | Yes | UH |  | property.post_desig | Varchar(40) |  |  | Road Number | TRUE | Road Number
Road Name 1 |  | Yes | UH |  | postcode.aline1 | Varchar(40) |  |  | Road Name 1 | TRUE | Road Name 1
Road Name 2 |  | Yes | UH |  | postcode.aline2 | Varchar(40) | Can also contain town |  | Road Name 2 | TRUE | Road Name 2
Town |  | Yes | UH |  | postcode.aline3 | Varchar(40) | Can also contain county |  | Town | TRUE | Town
County |  | Yes | UH |  | postcode.aline4 | Varchar(40) |  |  | County | TRUE | County
Postcode |  | Yes | UH |  | postcode.post_code | Varchar(10) |  |  | Postcode | TRUE | Postcode
Country Code |  | No | N/A |  |  | N/A |  |  | Country Code | TRUE | Country Code
Phone |  | No | N/A |  |  | Varchar(20) |  |  | Phone | TRUE | Phone
Property Type Code |  | No | N/A |  |  | 5 digit code (must exist in Bluebox) |  |  | Property Type Code | TRUE | Property Type Code
Location Code |  | Yes | UH |  | property.region | 5 digit code (must exist in Bluebox) |  |  | Location Code | TRUE | Location Code
Property Group Code |  | No | N/A |  |  | 5 digit code (must exist in Bluebox) |  |  | Property Group Code | TRUE | Property Group Code
Property Analysis Code |  | No | N/A |  |  | 5 digit code (must exist in Bluebox) |  |  | Property Analysis Code | TRUE | Property Analysis Code
Site Ref |  | No | N/A |  |  | 6 digit numeric ref |  |  | Site Ref | TRUE | Site Ref
Rating Authority Ref |  | Yes | UH |  | property.la_ref | 6 digit numeric ref (must exist in BB) | LA ref is alpha-numeric | Aren't these the same? | Rating Authority Ref | TRUE | Rating Authority Ref
Planning Authority Ref |  | Yes | UH |  | property.la_ref | 6 digit numeric ref (must exist in BB) | LA ref is alpha-numeric | Aren't these the same? | Planning Authority Ref | TRUE | Planning Authority Ref
Main Use Class |  | No | N/A |  | (poss Qube) | 17 hard coded options: - A1-A3, B1-B8, C1-C3, D1,D2 & SG |  |  | Main Use Class | TRUE | Main Use Class
Sub Use Class |  | No | N/A |  |  | Free form text |  |  | Sub Use Class | TRUE | Sub Use Class
Listed Building |  | Yes | UH |  | ? | Y or N | Not in UH. Legal team spreadsheet? |  | Listed Building | TRUE | Listed Building
Management Start Date |  | Yes | UH |  | ? | dd/mm/yyyy | Not in UH. Only shows current |  | Management Start Date | TRUE | Management Start Date
Management End Date |  | Yes | UH |  | ? | dd/mm/yyyy | Not in UH. Only shows current |  | Management End Date | TRUE | Management End Date
Year Constructed |  | Yes | UH |  | property.u_build_date | yyyy |  |  | Year Constructed | TRUE | Year Constructed
Year Last Refurbisehd |  | Yes | UH |  | property.handover | yyyy |  |  | Year Last Refurbisehd | TRUE | Year Last Refurbisehd
Our File Reference |  | Yes | UH |  | property.man_scheme | Varchar(20) |  |  | Our File Reference | TRUE | Our File Reference
Ext File Reference |  | Yes | UH |  | ? | Varchar(20) | Unsure of this one |  | Ext File Reference | TRUE | Ext File Reference
No Of Buildings |  | No | N/A |  |  | Numeric(4,0) |  |  | No Of Buildings | TRUE | No Of Buildings
No of Floors |  | Yes | UH |  | rent.floor_level | Numeric(4,0) | Max floor level from rent for unit? | Doesn't work | No of Floors | TRUE | No of Floors
Asbestos Present |  | Yes | UH |  | property.asbestos | Undetermined, Y or N |  |  | Asbestos Present | TRUE | Asbestos Present
Energy Efficiency Rating |  | Yes | Integrator |  | Integrator | Varchar(10) | Unsure of this one |  | Energy Efficiency Rating | TRUE | Energy Efficiency Rating
Description |  | No | N/A |  |  | Varchar(254) |  |  | Description | TRUE | Description
Management Company for S/C |  | Yes | UH |  | ? | Y or N |  |  | Management Company for S/C | TRUE | Management Company for S/C
Management Company Client Ref |  | Yes | UH |  | ? | Numeric(6,0) | Lookup the company ref based on UH supplying the UH company Ref |  | Management Company Client Ref | TRUE | Management Company Client Ref
Main Client Interest |  | Yes | UH |  |  | N/A | Default to 100 |  | Main Client Interest | TRUE | Main Client Interest
VAT Opted |  | Yes | Predefined | N | ? | Y or N |  |  | VAT Opted | TRUE | VAT Opted
VAT Opted Date |  | No | N/A |  |  | dd/mm/yyyy |  |  | VAT Opted Date | TRUE | VAT Opted Date
Percentage Rent VATable |  | No | N/A |  |  | Numeric(5,2) | Should enter 0 or 100 (default is 0) |  | Percentage Rent VATable | TRUE | Percentage Rent VATable
UPRN |  | No | N/A |  |  | Numeric(12,0) |  |  | UPRN | TRUE | UPRN
OS Ref |  | No | N/A |  |  | Varchar(10) |  |  | OS Ref | TRUE | OS Ref
OS Point Address Ref |  | No | N/A |  |  | Varchar(20) |  |  | OS Point Address Ref | TRUE | OS Point Address Ref
Easting/Northing |  | No | N/A |  |  | Numeric(12,0) |  |  | Easting/Northing | TRUE | Easting/Northing
Number of Workstations |  | No | N/A |  |  | Numeric(4,0) |  |  | Number of Workstations | TRUE | Number of Workstations
Head Count |  | No | N/A |  |  | Numeric(4,0) |  |  | Head Count | TRUE | Head Count
New Site Ref |  | No | N/A |  |  | Numeric(3,0) |  |  | New Site Ref | TRUE | New Site Ref
Property Status Code |  | Yes | UH |  | vmrecord.vm_propcond_stt | Varchar(10) | Status Category must exist in BB |  | Property Status Code | TRUE | Property Status Code
Property Status As At |  | Yes | UH |  | ? | dd/mm/yyyy | Doesn't appear on UH. |  | Property Status As At | TRUE | Property Status As At
Linked file Name |  | No | N/A |  |  | Text |  |  | Linked file Name | TRUE | Linked file Name
SC Expend VAT Recov |  | No | N/A |  |  | Numeric(5,2) | Should enter 0 or 100 (default is 0) |  | SC Expend VAT Recov | TRUE | SC Expend VAT Recov
Other Expend VAT Recov |  | No | N/A |  |  | Numeric(5,2) | Should enter 0 or 100 (default is 0) |  | Other Expend VAT Recov | TRUE | Other Expend VAT Recov
Estate Ref |  | Yes | Estate Table |  | property.u_estate | N/A | Lookup the Estate ref based on UH supplying the UH Estate Ref |  | Estate Ref | TRUE | Estate Ref
HA Earnings County Code |  | Yes | UH |  | ? | Varchar(5,0) | New. Code must exist in BB. |  | #N/A | #N/A

## Property Account
Can be generated from the property if Company Account in Place | Mandatory Field | Required (For OHG) | Source | Predefined Values | UH Field | Format | Comments
Property Ref
Base Currency Code
S/C Apportionment
S/C Frequency
S/C Expenditure VAT Recovery Perc
S/C Income Period Control
Stop All Postings
Stop Charge Raising
Stop Demand Production
Irish Vat Concession Applies
Apportionment Basis
Other Expenditure VAT Recovery Perc
Safety Margin
Suspense Bank Account Uri
Summary Balance Report Set Code
Separate Management Company Account
Independent Statement at Property Level
Date Type
Include All S/L Codes
S/L Code List
Include Blank S/L
Print Using Layout Template
Format Override Permitted
Automated Payments To Client
Pay To Client Transaction Type Code
Automated Management Fees
Separate Fee Account
Fee Start Date
Fee Last Run To Date
Demand Format Code
Demand Language Code
S/C Apportionment Level
VAT Recovery Calculation Basis
Debtor for Residual Liability
Residual Liability Trans Type Code
Residual Liability VAT Code
Service Charge Journal Usage
Commission Applies
Agent
Handling Account
Transaction Type
Eligible/Ineligible | [6 empty] | New

## Unit
|  | Mandatory Field | Required (For OHG) | Source | Predefined Values | UH Field | Format | Comments | New Int
Property Ref | Property_Ref | Yes | Yes | Property Table |  | property.prop_ref | N/A | Lookup the property ref based on UH supplying the UH property ref | Property Ref | TRUE | Property Ref
Ref | Ref | Yes | Yes | Auto Generate |  |  | N/A |  | Ref | TRUE | Ref
Name | Name | Yes | Yes | UH |  |  | Varchar(45) |  | Name | TRUE | Name
Manager Code | Manager Code | Yes | Yes | ? |  | ? | 5 digit code for the manager (code must exist in Bluebox) | If not available in UH then a default could be populated and the Manager Code Changed After loading (e.g. use Predefined manager code of 'New' then OHG can change it when the manager is known) | Manager Code | TRUE | Manager Code
Address Line 1 | Address_Line_1 |  | Yes | UH |  | househ.house_desc | Varchar(40) |  | Address Line 1 | TRUE | Address Line 1
Building Name | Building Name |  | Yes | UH |  | property.post_preamble | Varchar(40) |  | Building Name | TRUE | Building Name
Road Number | Road Number |  | Yes | UH |  | property.post_desig | Varchar(40) |  | Road Number | TRUE | Road Number
Road Name 1 | Road Name 1 |  | Yes | UH |  | postcode.aline1 | Varchar(40) |  | Road Name 1 | TRUE | Road Name 1
Road Name 2 | Road Name 2 |  | Yes | UH |  | postcode.aline2 | Varchar(40) | Can also contain town | Road Name 2 | TRUE | Road Name 2
Town | Town |  | Yes | UH |  | postcode.aline3 | Varchar(40) | Can also contain county | Town | TRUE | Town
County | County |  | Yes | UH |  | postcode.aline4 | Varchar(40) |  | County | TRUE | County
Postcode | Postcode |  | Yes | UH |  | postcode.post_code | Varchar(10) |  | Postcode | TRUE | Postcode
Country Code | Country_Code |  | No | N/A |  |  | N/A |  | Country Code | TRUE | Country Code
Search Name | Search Name |  | Yes | UH |  |  | Varchar(20) |  | Search Name | TRUE | Search Name
Tenure | Tenure |  | ? | UH |  | rent.tenure | Varchar(10) |  | Tenure | TRUE | Tenure
Whole of Property | Whole_of_Property |  | ? | UH |  | ? | Y or N |  | Whole of Property | TRUE | Whole of Property
Property Type Code | Property_Type_Code |  | ? | UH |  | property.cat_type | Varchar(5) | Code must exist in BB | Property Type Code | TRUE | Property Type Code
Location Code | Location Code |  | ? | UH |  | ? | Varchar(5) | Code must exist in BB | Location Code | TRUE | Location Code
Unit Group Code | Unit_Group_Code |  | ? | UH |  | ? | Varchar(5) | Code must exist in BB | Unit Group Code | TRUE | Unit Group Code
Property Analysis Code | Property_Analysis_Code |  | ? | UH |  | ? | Varchar(5) | Code must exist in BB | Property Analysis Code | TRUE | Property Analysis Code
Rating Authority Ref | Rating_Authority_Ref |  | ? | UH |  | ? | Numeric(6,0) | Authority ref must exist in BB | Rating Authority Ref | TRUE | Rating Authority Ref
Planning Authority Ref | Planning_Authority_Ref |  | ? | UH |  | ? | Numeric(6,0) | Authority ref must exist in BB | Planning Authority Ref | TRUE | Planning Authority Ref
Main Use Class | Main_Use_Class |  | ? | UH |  | ? | 17 hard coded options: - A1-A3, B1-B8, C1-C3, D1,D2 & SG |  | Main Use Class | TRUE | Main Use Class
Sub Use Class | Sub_Use_class |  | ? | UH |  | ? | Free form text |  | Sub Use Class | TRUE | Sub Use Class
Listed Building | Listed_Building |  | ? | UH |  | ? | Y or N | No on UH yet - Legal team? | Listed Building | TRUE | Listed Building
Management Start Date | Management_Start_Date |  | ? | UH |  | ? | dd/mm/yyyy | Not in UH. Only shows current | Management Start Date | TRUE | Management Start Date
Management End Date | Management_End_Date |  | ? | UH |  | ? | dd/mm/yyyy | Not in UH. Only shows current | Management End Date | TRUE | Management End Date
Year Constructed | Year_Constructed |  | ? | UH |  | property.u_build_date | yyyy |  | Year Constructed | TRUE | Year Constructed
Year Last Refurbished | Year_last_Refurbished |  | ? | UH |  | property.handover | yyyy |  | Year Last Refurbished | TRUE | Year Last Refurbished
Obsolete Unit | Obsolete_Unit |  | ? | UH |  | ? | Y or N |  | Obsolete Unit | TRUE | Obsolete Unit
UPRN | UPRN |  | ? | UH |  | property.prop_ref | Numeric(12,0) | Alpha-numeric + same as property ref? | UPRN | TRUE | UPRN
OS Ref | OS_Ref |  | ? | UH |  | ? | Varchar(10) | Not on UH | OS Ref | TRUE | OS Ref
OS Point Address Ref | OS_Point_Address_Ref |  | ? | UH |  | ? | Varchar(20) | Not on UH | OS Point Address Ref | TRUE | OS Point Address Ref
Easting/Northing | Easting_Northing |  | ? | UH |  | ? | Numeric(12,0) | Not on UH | Easting/Northing | TRUE | Easting/Northing
VAT Opted | VAT_Opted |  | ? | UH |  | ? | Y or N | Not on UH | VAT Opted | TRUE | VAT Opted
VAT Opted Date | VAT_Opted_Date |  | ? | UH |  | ? | dd/mm/yyyy | Not on UH | VAT Opted Date | TRUE | VAT Opted Date
Our File Ref | Our_File_ref |  | ? | UH |  | ? | Varchar(20) | Not on UH | Our File Ref | TRUE | Our File Ref
Ext File Reference | Ext_File_Reference |  | ? | UH |  | ? | Varchar(20) | Not on UH | Ext File Reference | TRUE | Ext File Reference
No of Floors | No_of_Floors |  | ? | UH |  | rent.floor_level | Numeric(4,0) | use MAX function - not working!!! | No of Floors | TRUE | No of Floors
Number of Workstations | Number_of_Workstations |  | ? | UH |  | ? | Numeric(4,0) | Not on UH | Number of Workstations | TRUE | Number of Workstations
Head Count | Head_Count |  | ? | UH |  | ? | Numeric(4,0) | Not on UH | Head Count | TRUE | Head Count
Description | Description |  | ? | UH |  | ? | Varchar(254) | Not on UH | Description | TRUE | Description
Head Lease Ref | Head_Lease_Ref |  | No | N/A |  | ? | N/A | Not on UH | Head Lease Ref | TRUE | Head Lease Ref
Photo File name | Photo_File_name |  | ? | UH |  | ? | Text | Not on UH | Photo File name | TRUE | Photo File name
Shared Ownership | Shared_Ownership |  | Yes | UH |  | property.cat_type | Y or N | New - cat_type = LH1 | #N/A | #N/A
% Owned by Tenant | %_Owned_by_Tenant |  | Yes | UH |  | rent.sharedowner | Numeric(5,2) | New | #N/A | #N/A
Permitted Number of People | Permitted_Number_of_People |  | Yes | UH |  | rent.perm_no | Numeric(2,0) | New | #N/A | #N/A
HA Earnings County | HA_Earnings_County |  | Yes | UH |  | ? | Varchar(5) | New. Code must exist in BB | #N/A | #N/A
Number of Bedrooms | Number_of_Bedrooms |  | Yes | UH |  | rent.no_beds | 0,1,2,3.4.5 or '6+' | New | #N/A | #N/A
Initial Valuation | Initial_Valuation |  | Yes | UH |  | rent.valuation | Numeric(9,0) | New - 1999 Valuation | #N/A | #N/A

## Tenant
|  | Mandatory Field | Required (For OHG) | Source | Predefined Values | UH Field | Format | Comments | New Int |  | dd
Ref | Ref | Yes | Yes | Auto Generate |  |  | N/A |  | Ref | TRUE | Ref
Name | Name | Yes | Yes | UH |  | member.forename + member.surname | Varchar(45) |  | Name | TRUE | Name
Search Name | Search Name |  | Yes | UH |  | (UH Tenant Ref) househ.house_ref | Varchar(20) |  | Search Name | TRUE | Search Name
Contact Name | Contact Name |  | Yes | UH |  | member.title + member.forename + member.surname | Varchar(45) |  | Contact Name | TRUE | Contact Name
Tenant Parent Ref | Tenant Parent Ref |  | Yes | UH |  | househ.house_ref + member.person_no | Numeric(6,0) | Tenant parent ref must exist in BB | Tenant Parent Ref | TRUE | Tenant Parent Ref
Building Name | Building Name |  | Yes | UH |  | property.post_preamble | Varchar(40) |  | Building Name | TRUE | Building Name
Road Number | Road Number |  | Yes | UH |  | property.post_desig | Varchar(40) |  | Road Number | TRUE | Road Number
Road Name 1 | Road Name 1 |  | Yes | UH |  | postcode.aline1 | Varchar(40) |  | Road Name 1 | TRUE | Road Name 1
Road Name 2 | Road Name 2 |  | Yes | UH |  | postcode.aline2 | Varchar(40) |  | Road Name 2 | TRUE | Road Name 2
Town | Town |  | Yes | UH |  | postcode.aline3 | Varchar(40) |  | Town | TRUE | Town
County | County |  | Yes | UH |  | postcode.aline4 | Varchar(40) |  | County | TRUE | County
Postcode | Postcode |  | Yes | UH |  | postcode.post_code | Varchar(10) |  | Postcode | TRUE | Postcode
Country Code | Country_Code |  | No | N/A |  |  | N/A |  | Country Code | TRUE | Country Code
Credit Rating | Credit Rating |  | Yes | UH |  | ? | Varchar(5) | Not in UH yet | Credit Rating | TRUE | Credit Rating
Covenant Strength | Covenant_Strength |  | No | N/A |  |  | Varchar(5) |  | Covenant Strength | TRUE | Covenant Strength
VAT Prefix | VAT_Prefix |  | No | N/A |  |  | Varchar(2) | i.e. GB | VAT Prefix | TRUE | VAT Prefix
VAT Reg No | VAT_Reg_No |  | No | N/A |  |  | Varchar(9) |  | VAT Reg No | TRUE | VAT Reg No
Reg Company No | Reg_Company_No |  | No | N/A |  |  | Varchar(12) |  | Reg Company No | TRUE | Reg Company No
Phone | Phone |  | Yes | UH |  | alan.contact_data_b.Telephone | Varchar(20) |  | Phone | TRUE | Phone
Direct Phone | Direct Phone |  | Yes | UH |  | ? | Varchar(20) | Will update table to reflect in future | Direct Phone | TRUE | Direct Phone
Mobile Phone | Mobile Phone |  | Yes | UH |  | alan.contact_data_b.Mobile | Varchar(20) |  | Mobile Phone | TRUE | Mobile Phone
Fax | Fax |  | Yes | UH |  | ? | Varchar(20) | Not in UH | Fax | TRUE | Fax
Email | Email |  | Yes | UH |  | alan.contact_data_b.Email | Varchar(50) | must be a single valid email - Need to update contact_data_b query so emails are included | Email | TRUE | Email
Remittance Contact Name | Remittance_Contact_Name |  | No | N/A |  |  | Varchar(45) |  | Remittance Contact Name | TRUE | Remittance Contact Name
Remittance Fax | Remittance_Fax |  | No | N/A |  |  | Varchar(20) |  | Remittance Fax | TRUE | Remittance Fax
Remittance Email | Remittance_Email |  | No | N/A |  |  | Varchar(50) | must be a single valid email | Remittance Email | TRUE | Remittance Email
Remittance Preferred Method of Contact | Remittance_Preferred_Method_of_contact |  | No | N/A |  |  | Post, Email or Fax |  | Remittance Preferred Method of Contact | TRUE | Remittance Preferred Method of Contact
Demands Contact Name | Demands_Contact_Name |  | No | N/A |  |  | Varchar(45) |  | Demands Contact Name | TRUE | Demands Contact Name
Demands Email | Demands_Email |  | No | N/A |  |  | Varchar(50) | must be a single valid email | Demands Email | TRUE | Demands Email
Demands Fax | Demands_Fax |  | No | N/A |  |  | Varchar(20) |  | Demands Fax | TRUE | Demands Fax
Demands Preferred Method of Contact | Demands_Preferred_Method_of_Contact |  | No | N/A |  |  | Post, Email or Fax |  | Demands Preferred Method of Contact | TRUE | Demands Preferred Method of Contact

## Lease
| Mandatory Field | Required (For OHG) | Source | Predefined Values | UH Field | Format | Comments |  | New Int |  | New Int
Ref | Yes | Yes | Auto Generate |  |  | N/A |  |  | Ref | TRUE | Ref
Property Ref | Yes | Yes | Property Table |  | property.man_scheme | N/A | Lookup the property ref based on UH supplying the UH Property Ref |  | Property Ref | TRUE | Property Ref
Unit Ref | Yes | Yes | Unit Table |  | property.prop_ref | N/A | Lookup the unit ref based on UH supplying the UH unit Ref |  | Unit Ref | TRUE | Unit Ref
Current Tenant Ref | Yes | Yes | Tenant Table |  | househ.house_ref | N/A | Lookup the Tenant ref based on UH supplying the UH Tenant Ref |  | Current Tenant Ref | TRUE | Current Tenant Ref
Term Start Date | Yes | Yes | UH |  | tenagree.cot | dd/mm/yyyy |  |  | Term Start Date | TRUE | Term Start Date
Term End Date | Yes | Yes | UH |  | tenagree.eot | dd/mm/yyyy |  |  | Term End Date | TRUE | Term End Date
SC VAT Code | Yes | Yes | UH |  | Not found | Varchar(5) | VAT code must exist in BB |  | SC VAT Code | TRUE | SC VAT Code
Rent VAT Code | Yes | Yes | UH |  | Not found | Varchar(5) | VAT code must exist in BB |  | Rent VAT Code | TRUE | Rent VAT Code
Default Currency Code | Yes | Yes | Predefined | GBP | Not found | N/A |  |  | Default Currency Code | TRUE | Default Currency Code
Use Alternative Currency for Rent | Yes | Yes | Predefined | N | Not found | N/A |  |  | Use Alternative Currency for Rent | TRUE | Use Alternative Currency for Rent
Recoverables VAT Code | Yes | Yes | UH |  | Not found | Varchar(5) | VAT code must exist in BB |  | Recoverables VAT Code | TRUE | Recoverables VAT Code
Tenant Related Contact Name |  | ? | UH |  |  | Varchar(45) | If field is needed then further development would be required (for the tenant related contact table) |  | Tenant Related Contact Name | TRUE | Tenant Related Contact Name
Lease Type Code |  | Yes | UH |  |  | Varchar(5) | Code must exist in BB |  | Lease Type Code | TRUE | Lease Type Code
Lease Term |  | ? | UH |  |  | Varchar(20) |  |  | Lease Term | TRUE | Lease Term
Open Lease |  | ? | UH |  |  | Y or N | N if left blank |  | Open Lease | TRUE | Open Lease
Lease Dated |  | ? | UH |  |  | dd/mm/yyyy |  |  | Lease Dated | TRUE | Lease Dated
Passing Rent |  | Yes | UH |  |  | Numeric(13,2) | Annual rent charge amount |  | Passing Rent | TRUE | Passing Rent
Alternative Currency Passing Rent |  | No | N/A |  |  | N/A |  |  | Alternative Currency Passing Rent | TRUE | Alternative Currency Passing Rent
Outside 1954 Act |  | Yes | UH |  |  | Y or N | Refer to Dan |  | Outside 1954 Act | TRUE | Outside 1954 Act
1987 Act Applies |  | Yes | UH |  |  | Y or N | Refer to Dan |  | 1987 Act Applies | TRUE | 1987 Act Applies
2002 Act Applies |  | Yes | UH |  |  | Y or N | Refer to Dan |  | 2002 Act Applies | TRUE | 2002 Act Applies
Privity Applies |  | No | N/A |  |  | Y or N |  |  | Privity Applies | TRUE | Privity Applies
Termination Status |  | Yes | UH |  |  | Current, Surrendered, Break, Merger, Notice, Disclaimer, Forfeiture, Others, Sold | 'Current' entered if left blank |  | Termination Status | TRUE | Termination Status
Terminated Date |  | Yes | UH |  |  | dd/mm/yyyy | Only required if termination status is not current | Same as eot? | Terminated Date | TRUE | Terminated Date
Review Basis |  | Yes | UH |  |  | 'N/A', Unspecified, Fixed review, Market review, Restricted, Turnover, Indexed, Other, (none) | For annual index linked reviews enter 'Indexed' |  | Review Basis | TRUE | Review Basis
Review Pattern |  | Yes | UH |  |  | Numeric(2,0) | Social rents will be '1' for an annual review |  | Review Pattern | TRUE | Review Pattern
Next Review Date |  | Yes | UH |  |  | dd/mm/yyyy | Social rents will be 1st April after next (so a new lease on 1/10/2014 would have a next review date of 01/04/2016) |  | Next Review Date | TRUE | Next Review Date
First Review Date |  | Yes | UH |  |  | dd/mm/yyyy | Weeklies = 07/04/2003 (check) , Monthlies = 01/04/2003 |  | First Review Date | TRUE | First Review Date
Review Notice Period |  | Yes | UH |  |  | Numeric(3,0) |  |  | Review Notice Period | TRUE | Review Notice Period
Review Notice Period Type |  | Yes | UH |  |  | Days or Months |  |  | Review Notice Period Type | TRUE | Review Notice Period Type
Breach Status |  | No | N/A |  |  | None, Full, Stop, Override |  |  | Breach Status | TRUE | Breach Status
Alternative Rent Currency Code |  | No | N/A |  |  | N/A |  |  | Alternative Rent Currency Code | TRUE | Alternative Rent Currency Code
Conversion Lead Time |  | No | N/A |  |  | N/A |  |  | Conversion Lead Time | TRUE | Conversion Lead Time
Rent Charge Type Code |  | Yes | UH |  | e.g. SC or RENT | Varchar(5) | Charge type code must exist in BB |  | Rent Charge Type Code | TRUE | Rent Charge Type Code
Rent Due Date Code |  | Yes | UH |  | e.g. WEEKL, M01 | Varchar(5) | Due date code must exist in BB |  | Rent Due Date Code | TRUE | Rent Due Date Code
Working Day of the Period |  | No | N/A |  |  | N/A |  |  | Working Day of the Period | TRUE | Working Day of the Period
Region Code |  | No | N/A |  |  | N/A |  |  | Region Code | TRUE | Region Code
Rent in Advance |  | Yes | UH |  |  | Y or N |  |  | Rent in Advance | TRUE | Rent in Advance
Rent Commence Date |  | Yes | UH |  |  | dd/mm/yyyy |  |  | Rent Commence Date | TRUE | Rent Commence Date
Turnover Rent |  | No | N/A |  |  | N/A |  |  | Turnover Rent | TRUE | Turnover Rent
Turnover Percentage |  | No | N/A |  |  | N/A |  |  | Turnover Percentage | TRUE | Turnover Percentage
Threshold |  | No | N/A |  |  | N/A |  |  | Threshold | TRUE | Threshold
VAT on Rent Applies |  | No | N/A |  |  | N/A |  |  | VAT on Rent Applies | TRUE | VAT on Rent Applies
Rent Terms |  | Yes | UH |  |  | Text Box |  |  | Rent Terms | TRUE | Rent Terms
Interest on Late Rent |  | No | N/A |  |  | N/A |  |  | Interest on Late Rent | TRUE | Interest on Late Rent
Late Rent Int From Due Date |  | No | N/A |  |  | N/A |  |  | Late Rent Int From Due Date | TRUE | Late Rent Int From Due Date
Late Rent Int Bank Code |  | No | N/A |  |  | N/A |  |  | Late Rent Int Bank Code | TRUE | Late Rent Int Bank Code
Late Rent Int Rate |  | No | N/A |  |  | N/A |  |  | Late Rent Int Rate | TRUE | Late Rent Int Rate
Late Rent Int Basis |  | No | N/A |  |  | N/A |  |  | Late Rent Int Basis | TRUE | Late Rent Int Basis
Days Grace On Late Rent |  | No | N/A |  |  | N/A |  |  | Days Grace On Late Rent | TRUE | Days Grace On Late Rent
Late Rent Min Int Rate |  | No | N/A |  |  | N/A |  |  | Late Rent Min Int Rate | TRUE | Late Rent Min Int Rate
Late Rent Max Int Rate |  | No | N/A |  |  | N/A |  |  | Late Rent Max Int Rate | TRUE | Late Rent Max Int Rate
Residential Use |  | Yes | UH |  |  | Y, N, Part, Not Applicable, (none) |  |  | Residential Use | TRUE | Residential Use
Registered Rent pa |  | Yes | UH |  |  | Numeric(13,2) |  |  | Registered Rent pa | TRUE | Registered Rent pa
Regulated Tenancy |  | No | N/A |  |  | Y or N |  |  | Regulated Tenancy | TRUE | Regulated Tenancy
Reg Rent Effective Date |  | Yes | UH |  |  | dd/mm/yyyy |  |  | Reg Rent Effective Date | TRUE | Reg Rent Effective Date
Review Notice Required |  | Yes | UH |  |  | Y or N |  |  | Review Notice Required | TRUE | Review Notice Required
Time Of Essence Clause |  | Yes | UH |  |  | Y or N |  |  | Time Of Essence Clause | TRUE | Time Of Essence Clause
Pre Expiry Review |  | No | N/A |  |  | Y or N |  |  | Pre Expiry Review | TRUE | Pre Expiry Review
Upwards Only Review |  | Yes | UH |  |  | Y or N |  |  | Upwards Only Review | TRUE | Upwards Only Review
Continue After Review |  | Yes | Predefined | Y |  | Y or N |  |  | Continue After Review | TRUE | Continue After Review
Interest on Late Review |  | No | N/A |  |  | N/A |  |  | Interest on Late Review | TRUE | Interest on Late Review
Late Review Min Int Rate |  | No | N/A |  |  | N/A |  |  | Late Review Min Int Rate | TRUE | Late Review Min Int Rate
Late Review Max Int Rate |  | No | N/A |  |  | N/A |  |  | Late Review Max Int Rate | TRUE | Late Review Max Int Rate
Late Review Bank Code |  | No | N/A |  |  | N/A |  |  | Late Review Bank Code | TRUE | Late Review Bank Code
Late Review Interest Rate |  | No | N/A |  |  | N/A |  |  | Late Review Interest Rate | TRUE | Late Review Interest Rate
Late Review Interest Basis |  | No | N/A |  |  | N/A |  |  | Late Review Interest Basis | TRUE | Late Review Interest Basis
Price Index Code |  | Yes | UH |  |  | Varchar(5) | Code must exist in BB. For Social Rents use 'TRI' |  | Price Index Code | TRUE | Price Index Code
Index Start Date |  | Yes | UH |  |  | dd/mm/yyyy | For Social rents use 1st April after next | Trace to confirm | Index Start Date | TRUE | Index Start Date
Index Month |  | No | N/A |  |  | N/A |  | Trace to confirm | Index Month | TRUE | Index Month
Index Due Date |  | ? | UH |  |  | Varchar(5) | Due date code must exist in BB | Trace to confirm | Index Due Date | TRUE | Index Due Date
Apportion First Uplift |  | ? | UH |  |  | Y or N |  | Trace to confirm | Apportion First Uplift | TRUE | Apportion First Uplift
Index Charged To Date |  | ? | UH |  |  | dd/mm/yyyy |  | Trace to confirm | Index Charged To Date | TRUE | Index Charged To Date
SC Charge Type Code |  | Yes | UH |  |  | Varchar(5) | Charge type code must exist in BB |  | SC Charge Type Code | TRUE | SC Charge Type Code
SC Due Date Code |  | Yes | UH |  |  | Varchar(5) | Due date code must exist in BB |  | SC Due Date Code | TRUE | SC Due Date Code
SC in Advance |  | Yes | UH |  |  | Y or N |  |  | SC in Advance | TRUE | SC in Advance
SC Commencement Date |  | Yes | UH |  |  | dd/mm/yyyy |  |  | SC Commencement Date | TRUE | SC Commencement Date
Annual SC |  | Yes | UH |  |  | Numeric(13,2) | Annual service charge amount |  | Annual SC | TRUE | Annual SC
SC Terms |  | Yes | UH |  |  | Text Box |  |  | SC Terms | TRUE | SC Terms
VAT on SC Applies |  | No | N/A |  |  | N/A |  |  | VAT on SC Applies | TRUE | VAT on SC Applies
Annual SC Adjustable |  | Yes | UH |  |  | Y or N |  |  | Annual SC Adjustable | TRUE | Annual SC Adjustable
Interest on Late SC |  | No | N/A |  |  | N/A |  |  | Interest on Late SC | TRUE | Interest on Late SC
Other Fixed Recoverables |  | No | N/A |  |  | N/A |  |  | Other Fixed Recoverables | TRUE | Other Fixed Recoverables
Late SC interest Bank Code |  | No | N/A |  |  | N/A |  |  | Late SC interest Bank Code | TRUE | Late SC interest Bank Code
Days Grace on Late SC |  | No | N/A |  |  | N/A |  |  | Days Grace on Late SC | TRUE | Days Grace on Late SC
Late SC Interest Rate |  | No | N/A |  |  | N/A |  |  | Late SC Interest Rate | TRUE | Late SC Interest Rate
Late SC Interest Basis |  | No | N/A |  |  | N/A |  |  | Late SC Interest Basis | TRUE | Late SC Interest Basis
Late SC Interest From Date |  | No | N/A |  |  | N/A |  |  | Late SC Interest From Date | TRUE | Late SC Interest From Date
Late SC Min Int Rate |  | No | N/A |  |  | N/A |  |  | Late SC Min Int Rate | TRUE | Late SC Min Int Rate
Late SC Max Int Rate |  | No | N/A |  |  | N/A |  |  | Late SC Max Int Rate | TRUE | Late SC Max Int Rate
SC Apportionment Start Date |  | Yes | UH |  |  | dd/mm/yyyy | Only required if not liable for the whole year. |  | SC Apportionment Start Date | TRUE | SC Apportionment Start Date
SC Apportionment Trans Type Code |  | Yes | UH |  |  | Varchar(5) | Transaction type code must exist in BB |  | SC Apportionment Trans Type Code | TRUE | SC Apportionment Trans Type Code
Inclusive Rent |  | Yes | UH |  |  | Y or N |  |  | Inclusive Rent | TRUE | Inclusive Rent
Int On Late Others |  | No | N/A |  |  | N/A |  |  | Int On Late Others | TRUE | Int On Late Others
Days Grace on Late Others |  | No | N/A |  |  | N/A |  |  | Days Grace on Late Others | TRUE | Days Grace on Late Others
Late Others Int Rate |  | No | N/A |  |  | N/A |  |  | Late Others Int Rate | TRUE | Late Others Int Rate
Late Others Int Basis |  | No | N/A |  |  | N/A |  |  | Late Others Int Basis | TRUE | Late Others Int Basis
Late Others Int From Due Date |  | No | N/A |  |  | N/A |  |  | Late Others Int From Due Date | TRUE | Late Others Int From Due Date
Late Others Int Bank Code |  | No | N/A |  |  | N/A |  |  | Late Others Int Bank Code | TRUE | Late Others Int Bank Code
Late Others Max Int Rate |  | No | N/A |  |  | N/A |  |  | Late Others Max Int Rate | TRUE | Late Others Max Int Rate
Late Others Min Int Rate |  | No | N/A |  |  | N/A |  |  | Late Others Min Int Rate | TRUE | Late Others Min Int Rate
Assignment Permitted |  | No | N/A |  |  | Y or N |  |  | Assignment Permitted | TRUE | Assignment Permitted
Assignment Terms |  | No | N/A |  |  | Text Box |  |  | Assignment Terms | TRUE | Assignment Terms
Subletting Permitted |  | No | N/A |  |  | Y or N |  |  | Subletting Permitted | TRUE | Subletting Permitted
Subletting Terms |  | No | N/A |  |  | Text Box |  |  | Subletting Terms | TRUE | Subletting Terms
Alterations Permitted |  | No | N/A |  |  | Y or N |  |  | Alterations Permitted | TRUE | Alterations Permitted
Alterations Terms |  | No | N/A |  |  | Text Box |  |  | Alterations Terms | TRUE | Alterations Terms
Restrictive Covenants |  | No | N/A |  |  | Y or N |  |  | Restrictive Covenants | TRUE | Restrictive Covenants
RC Terms |  | No | N/A |  |  | Text Box |  |  | RC Terms | TRUE | RC Terms
Change of Use Permitted |  | No | N/A |  |  | Y or N |  |  | Change of Use Permitted | TRUE | Change of Use Permitted
COU Terms |  | No | N/A |  |  | Text Box |  |  | COU Terms | TRUE | COU Terms
User Clause |  | No | N/A |  |  | Text Box |  |  | User Clause | TRUE | User Clause
Stay Open Clause |  | No | N/A |  |  | Y or N |  |  | Stay Open Clause | TRUE | Stay Open Clause
Our File Ref |  | Yes | UH |  | (UH Tenant Ref) | Varchar(20) |  |  | Our File Ref | TRUE | Our File Ref
Ext File Ref |  | No | N/A |  |  | Varchar(20) |  |  | Ext File Ref | TRUE | Ext File Ref
Resp for Int Rep |  | Yes | UH |  |  | Landlord, Tenant, N/A, Shared, (none) |  |  | Resp for Int Rep | TRUE | Resp for Int Rep
Resp for Ext Rep |  | Yes | UH |  |  | Landlord, Tenant, N/A, Shared, (none) |  |  | Resp for Ext Rep | TRUE | Resp for Ext Rep
Resp for Build Ins |  | Yes | UH |  |  | Landlord, Tenant, N/A, Shared, (none) |  |  | Resp for Build Ins | TRUE | Resp for Build Ins
Resp for LOR Ins |  | Yes | UH |  |  | Landlord, Tenant, N/A, Shared, (none) |  |  | Resp for LOR Ins | TRUE | Resp for LOR Ins
Resp for PL Ins |  | Yes | UH |  |  | Landlord, Tenant, N/A, Shared, (none) |  |  | Resp for PL Ins | TRUE | Resp for PL Ins
Resp for Plate Glass Ins |  | Yes | UH |  |  | Landlord, Tenant, N/A, Shared, (none) |  |  | Resp for Plate Glass Ins | TRUE | Resp for Plate Glass Ins
Resp for Rates |  | Yes | UH |  |  | Landlord, Tenant, N/A, Shared, (none) |  |  | Resp for Rates | TRUE | Resp for Rates
Resp for Int Decs |  | Yes | UH |  |  | Landlord, Tenant, N/A, Shared, (none) |  |  | Resp for Int Decs | TRUE | Resp for Int Decs
Int Decs First Year |  | No | N/A |  |  | yyyy |  |  | Int Decs First Year | TRUE | Int Decs First Year
Int Decs Frequency |  | No | N/A |  |  | Numeric(2,0) |  |  | Int Decs Frequency | TRUE | Int Decs Frequency
Resp for Ext Decs |  | Yes | UH |  |  | Landlord, Tenant, N/A, Shared, (none) |  |  | Resp for Ext Decs | TRUE | Resp for Ext Decs
Ext Decs First year |  | No | N/A |  |  | yyyy |  |  | Ext Decs First year | TRUE | Ext Decs First year
Ext Decs Fequency |  | No | N/A |  |  | Numeric(2,0) |  |  | Ext Decs Fequency | TRUE | Ext Decs Fequency
Demise |  | No | N/A |  |  | Text Box |  |  | Demise | TRUE | Demise
Landlord Party to Lease |  | No | N/A |  |  | Varchar(120) |  |  | Landlord Party to Lease | TRUE | Landlord Party to Lease
Tenant Party to Lease |  | No | N/A |  |  | Varchar(120) |  |  | Tenant Party to Lease | TRUE | Tenant Party to Lease
Plan File Name |  | No | N/A |  |  | Text |  |  | Plan File Name | TRUE | Plan File Name
Plan Date |  | No | N/A |  |  | dd/mm/yyyy |  |  | Plan Date | TRUE | Plan Date
Option First Date 1 |  | No | N/A |  |  | N/A |  |  | Option First Date 1 | TRUE | Option First Date 1
Option By 1 |  | No | N/A |  |  | N/A |  |  | Option By 1 | TRUE | Option By 1
Option 1 Notice Period |  | No | N/A |  |  | N/A |  |  | Option 1 Notice Period | TRUE | Option 1 Notice Period
Option 1 Notice Period Type |  | No | N/A |  |  | N/A |  |  | Option 1 Notice Period Type | TRUE | Option 1 Notice Period Type
Option 1 Min Notice Period |  | No | N/A |  |  | N/A |  |  | Option 1 Min Notice Period | TRUE | Option 1 Min Notice Period
Option 1 Min Notice Period Type |  | No | N/A |  |  | N/A |  |  | Option 1 Min Notice Period Type | TRUE | Option 1 Min Notice Period Type
Option Last Date 1 |  | No | N/A |  |  | N/A |  |  | Option Last Date 1 | TRUE | Option Last Date 1
Option Term 1 |  | No | N/A |  |  | N/A |  |  | Option Term 1 | TRUE | Option Term 1
Option Type Code 2 |  | No | N/A |  |  | N/A |  |  | Option Type Code 2 | TRUE | Option Type Code 2
Option First Date 2 |  | No | N/A |  |  | N/A |  |  | Option First Date 2 | TRUE | Option First Date 2
Option By 2 |  | No | N/A |  |  | N/A |  |  | Option By 2 | TRUE | Option By 2
Option 2 Notice Period |  | No | N/A |  |  | N/A |  |  | Option 2 Notice Period | TRUE | Option 2 Notice Period
Option 2 Notice Period Type |  | No | N/A |  |  | N/A |  |  | Option 2 Notice Period Type | TRUE | Option 2 Notice Period Type
Option 2 Min Notice Period |  | No | N/A |  |  | N/A |  |  | Option 2 Min Notice Period | TRUE | Option 2 Min Notice Period
Option 2 Min Notice Period Type |  | No | N/A |  |  | N/A |  |  | Option 2 Min Notice Period Type | TRUE | Option 2 Min Notice Period Type
Option Last Date 2 |  | No | N/A |  |  | N/A |  |  | Option Last Date 2 | TRUE | Option Last Date 2
Option Term 2 |  | No | N/A |  |  | N/A |  |  | Option Term 2 | TRUE | Option Term 2
Option Type Code 3 |  | No | N/A |  |  | N/A |  |  | Option Type Code 3 | TRUE | Option Type Code 3
Option First Date 3 |  | No | N/A |  |  | N/A |  |  | Option First Date 3 | TRUE | Option First Date 3
Option By 3 |  | No | N/A |  |  | N/A |  |  | Option By 3 | TRUE | Option By 3
Option 3 Notice Period |  | No | N/A |  |  | N/A |  |  | Option 3 Notice Period | TRUE | Option 3 Notice Period
Option 3 Notice Period Type |  | No | N/A |  |  | N/A |  |  | Option 3 Notice Period Type | TRUE | Option 3 Notice Period Type
Option 3 Min Notice Period |  | No | N/A |  |  | N/A |  |  | Option 3 Min Notice Period | TRUE | Option 3 Min Notice Period
Option 3 Min Notice Period Type |  | No | N/A |  |  | N/A |  |  | Option 3 Min Notice Period Type | TRUE | Option 3 Min Notice Period Type
Option Last Date 3 |  | No | N/A |  |  | N/A |  |  | Option Last Date 3 | TRUE | Option Last Date 3
Option Term 3 |  | No | N/A |  |  | N/A |  |  | Option Term 3 | TRUE | Option Term 3
Option Type Code 4 |  | No | N/A |  |  | N/A |  |  | Option Type Code 4 | TRUE | Option Type Code 4
Option First Date 4 |  | No | N/A |  |  | N/A |  |  | Option First Date 4 | TRUE | Option First Date 4
Option By 4 |  | No | N/A |  |  | N/A |  |  | Option By 4 | TRUE | Option By 4
Option 4 Notice Period |  | No | N/A |  |  | N/A |  |  | Option 4 Notice Period | TRUE | Option 4 Notice Period
Option 4 Notice Period Type |  | No | N/A |  |  | N/A |  |  | Option 4 Notice Period Type | TRUE | Option 4 Notice Period Type
Option 4 Min Notice Period |  | No | N/A |  |  | N/A |  |  | Option 4 Min Notice Period | TRUE | Option 4 Min Notice Period
Option 4 Min Notice Period Type |  | No | N/A |  |  | N/A |  |  | Option 4 Min Notice Period Type | TRUE | Option 4 Min Notice Period Type
Option Last Date 4 |  | No | N/A |  |  | N/A |  |  | Option Last Date 4 | TRUE | Option Last Date 4
Option Term 4 |  | No | N/A |  |  | N/A |  |  | Option Term 4 | TRUE | Option Term 4
Option Type Code 5 |  | No | N/A |  |  | N/A |  |  | Option Type Code 5 | TRUE | Option Type Code 5
Option First Date 5 |  | No | N/A |  |  | N/A |  |  | Option First Date 5 | TRUE | Option First Date 5
Option By 5 |  | No | N/A |  |  | N/A |  |  | Option By 5 | TRUE | Option By 5
Option 5 Notice Period |  | No | N/A |  |  | N/A |  |  | Option 5 Notice Period | TRUE | Option 5 Notice Period
Option 5 Notice Period Type |  | No | N/A |  |  | N/A |  |  | Option 5 Notice Period Type | TRUE | Option 5 Notice Period Type
Option 5 Min Notice Period |  | No | N/A |  |  | N/A |  |  | Option 5 Min Notice Period | TRUE | Option 5 Min Notice Period
Option 5 Min Notice Period Type |  | No | N/A |  |  | N/A |  |  | Option 5 Min Notice Period Type | TRUE | Option 5 Min Notice Period Type
Option Last Date 5 |  | No | N/A |  |  | N/A |  |  | Option Last Date 5 | TRUE | Option Last Date 5
Option Term 5 |  | No | N/A |  |  | N/A |  |  | Option Term 5 | TRUE | Option Term 5
Scottish Lease |  | No | N/A |  |  | N/A |  |  | Scottish Lease | TRUE | Scottish Lease
Rent Charged To Date |  | Yes | UH |  | (to start with use 31/03/2015) | dd/mm/yyyy | BB will raise charges from the day after this date |  | Rent Charged To Date | TRUE | Rent Charged To Date
SC Charged To Date |  | Yes | UH |  | (to start with use 31/03/2015) | dd/mm/yyyy | BB will raise charges from the day after this date |  | SC Charged To Date | TRUE | SC Charged To Date
Rent Transaction Type Code |  | Yes | UH |  |  | Varchar(5) | Transaction type code must exist in BB |  | Rent Transaction Type Code | TRUE | Rent Transaction Type Code
SC Transaction Type Code |  | Yes | UH |  |  | Varchar(5) | Transaction type code must exist in BB |  | SC Transaction Type Code | TRUE | SC Transaction Type Code
Guarantor |  | No | N/A |  |  | Y or N |  |  | Guarantor | TRUE | Guarantor
first_guarantee_type |  | No | N/A |  |  | Statutory Deposit or Guarantee |  |  | first_guarantee_type | TRUE | first_guarantee_type
first_guarantor_amount |  | No | N/A |  |  | Numeric(12,2) |  |  | first_guarantor_amount | TRUE | first_guarantor_amount
first_guarantor_start_date |  | No | N/A |  |  | dd/mm/yyyy |  |  | first_guarantor_start_date | TRUE | first_guarantor_start_date
first_guarantor_end_date |  | No | N/A |  |  | dd/mm/yyyy |  |  | first_guarantor_end_date | TRUE | first_guarantor_end_date
first_guarantor_cash_document |  | No | N/A |  |  | Document or Cash |  |  | first_guarantor_cash_document | TRUE | first_guarantor_cash_document
second_guarantee_type |  | No | N/A |  |  | Statutory Deposit or Guarantee |  |  | second_guarantee_type | TRUE | second_guarantee_type
second_guarantor_amount |  | No | N/A |  |  | Numeric(12,2) |  |  | second_guarantor_amount | TRUE | second_guarantor_amount
second_guarantor_start_date |  | No | N/A |  |  | dd/mm/yyyy |  |  | second_guarantor_start_date | TRUE | second_guarantor_start_date
second_guarantor_end_date |  | No | N/A |  |  | dd/mm/yyyy |  |  | second_guarantor_end_date | TRUE | second_guarantor_end_date
second_guarantor_cash_document |  | No | N/A |  |  | Document or Cash |  |  | second_guarantor_cash_document | TRUE | second_guarantor_cash_document
Social Rent Applies |  | Yes | UH |  |  | Y or N | New - Soc Rent Tab |  | #N/A | #N/A
Development Agreement |  | Yes | UH |  |  | Y or N | New - Soc Rent Tab |  | #N/A | #N/A
Household Income (p.a.) |  | Yes | UH |  |  | Numeric(7,0) | New - Soc Rent Tab |  | #N/A | #N/A
% Tolerance |  | Yes | UH |  |  | Numeric(5,2) | New - Soc Rent Tab |  | #N/A | #N/A
Set as Passing Rent |  | No | N/A |  |  | N/A | New - Soc Rent Tab |  | #N/A | #N/A
Development Agreement Terms |  | Yes | UH |  |  | Text Box | New - S/Chg Tab |  | #N/A | #N/A
Eligible S/C |  | Yes | UH |  |  | Numeric(13,2) | New - S/Chg Tab |  | #N/A | #N/A
Ineligible S/C |  | Yes | UH |  |  | Numeric(13,2) | New - S/Chg Tab |  | #N/A | #N/A
Delayed S/C Balancing |  | Yes | UH |  |  | Y or N | New - S/Chg Tab |  | #N/A | #N/A
Additional % per uplift |  | Yes | UH |  |  | Numeric(5,2) | New - Indeaxtion 1 Tab |  | #N/A | #N/A
Apply at least Minimum increase |  | Yes | UH |  |  | Y or N | New - Indeaxtion 1 Tab |  | #N/A | #N/A
Exclude Part Period Uplift |  | Yes | UH |  |  | Y or N | New - Indeaxtion 2 Tab |  | #N/A | #N/A

## Debtor
Can be generated from the Lease import | Mandatory Field | Required (For OHG) | Source | Predefined Values | UH Field | Format | Comments | New Int |  | newint
account_no | [7 empty] | account_no | TRUE | account_no
type | [7 empty] | type | TRUE | type
lease_ref | [7 empty] | lease_ref | TRUE | lease_ref
tenant_ref | [7 empty] | tenant_ref | TRUE | tenant_ref
invoice_required | [7 empty] | invoice_required | TRUE | invoice_required
billing_name | [7 empty] | billing_name | TRUE | billing_name
search_name | [7 empty] | search_name | TRUE | search_name
building_name | [7 empty] | building_name | TRUE | building_name
road_number | [7 empty] | road_number | TRUE | road_number
road_name_1 | [7 empty] | road_name_1 | TRUE | road_name_1
road_name_2 | [7 empty] | road_name_2 | TRUE | road_name_2
town | [7 empty] | town | TRUE | town
county | [7 empty] | county | TRUE | county
postcode | [7 empty] | postcode | TRUE | postcode
demand_language_code | [7 empty] | demand_language_code | TRUE | demand_language_code
debtor_category_code | [7 empty] | debtor_category_code | TRUE | debtor_category_code
stop_flag | [7 empty] | stop_flag | TRUE | stop_flag
address_category_code | [7 empty] | address_category_code | TRUE | address_category_code
billing_currency_code | [7 empty] | billing_currency_code | TRUE | billing_currency_code
arrears_letter | [7 empty] | arrears_letter | TRUE | arrears_letter
days_to_overdue | [7 empty] | days_to_overdue | TRUE | days_to_overdue
credit_rating | [7 empty] | credit_rating | TRUE | credit_rating
phone | [7 empty] | phone | TRUE | phone
direct_phone | [7 empty] | direct_phone | TRUE | direct_phone
mobile_phone | [7 empty] | mobile_phone | TRUE | mobile_phone
fax | [7 empty] | fax | TRUE | fax
contact_name | [7 empty] | contact_name | TRUE | contact_name
e_mail | [7 empty] | e_mail | TRUE | e_mail
vat_prefix | [7 empty] | vat_prefix | TRUE | vat_prefix
vat_reg_no | [7 empty] | vat_reg_no | TRUE | vat_reg_no
registered_company_no | [7 empty] | registered_company_no | TRUE | registered_company_no
use_for_auto_charges | [7 empty] | use_for_auto_charges | TRUE | use_for_auto_charges
usual_payment_method | [7 empty] | usual_payment_method | TRUE | usual_payment_method
final_demands | [7 empty] | final_demands | TRUE | final_demands
turnover_contact_name | [7 empty] | turnover_contact_name | TRUE | turnover_contact_name
country_code | [7 empty] | country_code | TRUE | country_code
debtor_for | [7 empty] | debtor_for | TRUE | debtor_for
s_c_bal_debtor | [7 empty] | s_c_bal_debtor | TRUE | s_c_bal_debtor
suppress_debtor_in_enquiries_flag | [7 empty] | suppress_debtor_in_enquiries_flag | TRUE | suppress_debtor_in_enquiries_flag
send_sms_with_arrears_letter | [7 empty] | send_sms_with_arrears_letter | TRUE | send_sms_with_arrears_letter
remittance_contact_name | [7 empty] | remittance_contact_name | TRUE | remittance_contact_name
remittance_fax | [7 empty] | remittance_fax | TRUE | remittance_fax
remittance_e_mail | [7 empty] | remittance_e_mail | TRUE | remittance_e_mail
remittance_preferred_method_of_contact | [7 empty] | remittance_preferred_method_of_contact | TRUE | remittance_preferred_method_of_contact
demands_contact_name | [7 empty] | demands_contact_name | TRUE | demands_contact_name
demands_fax | [7 empty] | demands_fax | TRUE | demands_fax
demands_e_mail | [7 empty] | demands_e_mail | TRUE | demands_e_mail
demands_preferred_method_of_contact | [7 empty] | demands_preferred_method_of_contact | TRUE | demands_preferred_method_of_contact

## Creditor
| Mandatory Field | Required (For OHG) | Source | Predefined Values | PIP/Sun Field | Format | Comments
Account No | Yes | Yes | Auto Generate |  |  | N/A
Type | Yes | Yes | Predefined | Supplier |  | N/A
Linked Creditor Ref |  | No | N/A |  |  | N/A | If no value entered here then a supplier record will be generated
Lease Ref |  | No | N/A |  |  | N/A | Not Required for Supplier Creditors
Name | Yes | Yes | SUN |  |  | Varchar(45)
Bank Country Code | Yes | Yes | Predefined | GB |  | N/A
Account Name | Yes | Yes | SUN |  |  | Varchar(45)
Default Currency Code | Yes | Yes | Predefined | GBP |  | N/A
Direct To Client |  | No | N/A |  |  | N/A
Search Name |  | Yes | SUN |  | (PIP Supplier Ref) | Varchar(20)
VAT prefix |  | Yes | SUN |  |  | Varchar(2) | i.e. GB
VAT Reg No |  | Yes | SUN |  |  | Varchar(9)
Registered Co No |  | Yes | SUN |  |  | Varchar(12)
Building Name |  | Yes | SUN |  |  | Varchar(40)
Road Number |  | Yes | SUN |  |  | Varchar(40)
Road Name 1 |  | Yes | SUN |  |  | Varchar(40)
Road Name 2 |  | Yes | SUN |  |  | Varchar(40)
Town |  | Yes | SUN |  |  | Varchar(40)
County |  | Yes | SUN |  |  | Varchar(40)
Postcode |  | Yes | SUN |  |  | Varchar(10)
Country Code |  | No | N/A |  |  | N/A
Address Category |  | No | N/A |  |  | N/A
Usual Payment method |  | No | N/A |  |  | N/A | Will default to cheque.
Bank Identifier |  | No | N/A |  |  | N/A
Bank Name |  | No | N/A |  |  | N/A
Bank Town |  | No | N/A |  |  | N/A
Sort Code |  | No | N/A |  |  | N/A
BIC Code |  | No | N/A |  |  | N/A
Account Number |  | No | N/A |  |  | N/A
IBAN Number |  | No | N/A |  |  | N/A
Roll Number |  | No | N/A |  |  | N/A
RIB Code |  | No | N/A |  |  | N/A
Short Account Name |  | Yes | SUN |  |  | Varchar(18) | Can use the first 18 digits of the name.
Priority |  | No | N/A |  |  | N/A
Stop Flag |  | Yes | SUN |  |  | Y or N
Payment Term Days |  | No | N/A |  |  | N/A
Payment Terms Day of month |  | No | N/A |  |  | N/A
Payment Terms Days After End Of Month |  | No | N/A |  |  | N/A
BACS Payment Reference |  | No | N/A |  |  | N/A
DUNS Number |  | No | N/A |  |  | N/A
Creditor Category |  | No | N/A |  |  | N/A
Payment Sel Service Type Code |  | No | N/A |  |  | N/A
Supplier Service Type Code |  | No | N/A |  |  | N/A
POM Export of Approved Orders |  | No | N/A |  |  | N/A
Suppress In Enquiries And Lookups |  | No | N/A |  |  | N/A
Contact Name |  | Yes | SUN |  |  | N/A
Phone No |  | Yes | SUN |  |  | Varchar(20)
Direct Phone No |  | Yes | SUN |  |  | Varchar(20)
Mobile Phone No |  | Yes | SUN |  |  | Varchar(20)
Fax No |  | Yes | SUN |  |  | Varchar(20)
Email |  | Yes | SUN |  |  | Varchar(45) | Must be a single valid email address
Remittance Contact Name |  | No | N/A |  |  | N/A
Remittance Email |  | No | N/A |  |  | N/A
Remittance Fax |  | No | N/A |  |  | N/A
Remittance Preferred Method of Contact |  | No | N/A |  |  | N/A
Ad-hoc Contact Name |  | No | N/A |  |  | N/A
Ad-hoc Email |  | No | N/A |  |  | N/A
Ad-hoc Fax |  | No | N/A |  |  | N/A
Ad-hoc Preferred Method of Contact |  | No | N/A |  |  | N/A
CIS Applies |  | No | N/A |  |  | Y or N
Subcontractor Type |  | No | N/A |  |  | Company, Partner or Sole-trader
Deduction Type |  | No | N/A |  |  | None, Standard or Higher
Unique Taxpayer Reference |  | No | N/A |  |  | Numeric(10)
Company Registration Number |  | No | N/A |  |  | Varchar(8)
National Insurance No |  | No | N/A |  |  | Varchar(9)
Approved Creditor |  | No | N/A |  |  | N/A

## Document Logging
| Mandatory Field | Required (For OHG) | Source | Predefined Values | PIP Field | Format | Comments
Property Ref |  | Yes | Property table |  |  | N/A | Lookup the property ref based on UH supplying the UH property ref
Authorising Manager Code |  | ? | PIP |  |  | Varchar(5) | Manager code must exist in BB
Account No | Yes | Yes | Creditor Table |  |  | N/A | Lookup the Account No based on UH supplying the UH supplier ref
Document Type | Yes | Yes | PIP |  |  | Varchar(5) | Code must exist in BB (of category 'Narrative') E.G Invoice or Credit Note (INV CRNOT)
Invoice Date | Yes | Yes | PIP |  | PIPLive.InvoiceHeader.[Inv Date] | dd/mm/yyyy
Invoice Reference | Yes | Yes | PIP |  | PIPLive.InvoiceHeader.[Inv Ref] | Varchar(35)
Net Amount | Yes | Yes | PIP |  | PIPLive.InvoiceHeader.InvoiceAmount | Numeric(12,2)
VAT Rate Code | Yes | Yes | PIP |  | PIPLive.InvoiceLines.AnalysisCode7 | Varchar(5) | Code must exist in BB
Scanned Invoice URL |  | Yes | PIP |  | ? | Text | Trace to confirm
Office Code |  | No | N/A |  |  | N/A
Log Status | Yes | Yes | PIP |  | PIPLive.InvoiceLines.LineStatus | Logged or Returned
Document Passed To |  | Yes | PIP |  |  | Varchar(5) | Manager code must exist in BB
Payment Due Date |  | Yes | PIP |  |  | dd/mm/yyyy
From Date |  | Yes | PIP |  |  | dd/mm/yyyy
To Date |  | Yes | PIP |  |  | dd/mm/yyyy
VAT Amount |  | Yes | PIP |  |  | Numeric(12,2)
Narrative |  | Yes | PIP |  |  | Varchar(40)
Scanned File Location |  | Yes | PIP |  |  | text | Trace to confirm

## Lease Expiry Task
Lease Expiry Task | Mandatory Field | Required (For OHG) | Source | Predefined Values | UH Field | Format | Comments

## Lease Assignment Task
Mandatory Field | Required (For OHG) | Source | Predefined Values | UH Field | Format | Comments